## Sheet1
Estimate | TimeSpend | Planned For | Type | ID | Summary | Owner | State
| 2 hours | Designer Rev1.14.0 Sprint3 | Task | 584033 | [RD-DEV][For Config team](專案管理) icon灰色时,鼠标移至，也可显示提示 | KAKA.WU 吳思言 | Resolved
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 583940 | [RD_DEV] 網路視圖在特定操作下刪除總線網路會發生線段殘留現象 | CLONE.LIN 林俊淵 | Completed
| 2 hours | Designer Rev1.14.0 Sprint3 | Task | 583901 | [RD-DEV][JIRA] (調適) [IABGVOC-1685] 示波器工具列圖示調整 | KAKA.WU 吳思言 | Completed
|  | Rev1.14.0 DIADesigner | Task | 583893 | [RD_DEV](網路配置) 網路通訊總線變更名稱後會殘留舊名稱的總線網路 | NANCY.TC.YANG 楊采真 | Resolved
|  | Designer Rev1.14.0 Sprint3 | Task | 583872 | [RD_DEV](上下載管理員)加入HMI裝置後，上下載管理員無法開啟&開始傳輸按鈕邏輯修正 | JANET.JC.CHEN 陳美蓁 | Resolved
| 1 hour 36 secs | Designer Rev1.14.0 Sprint3 | Task | 583762 | [RD-DEV](專案管理)更換匯出匯入ICON | KAKA.WU 吳思言 | Completed
|  | Rev1.14.0 DIADesigner | Task | 583760 | [RD_DEV](網路配置) 未開啟網路視圖時先新增裝置再開啟網路視圖建立Modbus連線後其總線的網路參數連動功能行為異常 | NANCY.TC.YANG 楊采真 | Completed
30 mins | 3 mins | Designer Rev1.14.0 Sprint3 | Task | 583575 | [RD_DEV] 新增 DIO 調機 Icon | ARCHIE.YANG 楊浩群 | Completed
1 hour | 24 mins | Designer Rev1.14.0 Sprint3 | Task | 583543 | [RD_DEV] 開啟通訊設定視窗時更新專案樹呈現的裝置連線狀況 | ARCHIE.YANG 楊浩群 | Completed
4 hours | 3 hours 18 mins | Designer Rev1.14.0 Sprint3 | Task | 583532 | [RD_DEV] 新增不做資料處理的 ModbusProtocolBase，新增可自訂 IConnector 的 Ethernet 設定物件 | ARCHIE.YANG 楊浩群 | Completed
2 hours | 1 hour 54 mins | Designer Rev1.14.0 Sprint3 | Task | 583509 | [RD_DEV] ETH 通訊設定改用統一的 Element Name 儲存 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 51 mins | Designer Rev1.14.0 Sprint3 | Task | 583499 | [RD_DEV] 調整 ASD Run/Stop 狀態訊息為 Servo On/Off | ARCHIE.YANG 楊浩群 | Completed
| 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 583357 | [RD_DEV] (DDF)W3A DDF示波器功能新增軸號區段與相關屬性 | MILENA.CHEN 陳孟歆 | Completed
| 3 hours 12 mins | Designer Rev1.14.0 Sprint3 | Task | 583294 | [RD_DEV](硬體配置) RTU 使用LC校正精靈沒接外部電源時，上下載會出現通訊錯誤的訊息，需優化提示訊息 | JANET.JC.CHEN 陳美蓁 | Completed
16 hours | 8 hours | Designer Rev1.14.0 Sprint3 | Task | 583237 | [RD_DEV]ECAT 掃描更新事件 | WILLIAM.HC.SHEN 沈桓慶 | Resolved
| 2 hours 6 mins | Designer Rev1.14.0 Sprint3 | Task | 583232 | [RD_DEV](專案管理) 當專案存檔路徑為網路路徑且無存讀權限時， 軟體被拒絕後就會crash(無法操作) | JANET.JC.CHEN 陳美蓁 | Completed
|  | Rev1.14.0 DIADesigner | Task | 583212 | [RD_DEV] AS00SCM-A 新增參數，更新 DDF | MILENA.CHEN 陳孟歆 | Assigned
| 2 hours | Designer Rev1.14.0 Sprint3 | Task | 583009 | [PLM] PJ134A-26-SS3-4-2-02-12_SE-SDD II (Detail Design)(4-2 SE-SDDD) | JEAN.LC.WANG 王儷臻 | Resolved
4 hours | 3 hours | Designer Rev1.14.0 Sprint2 | Task | 582732 | [RD_DEV] MX300 keypad 取值失敗時不應清空數值及單位 | JENNY.HY.CHEN 陳湘筠 | Completed
| 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 582613 | [RD_DEV] CANopen: Third Party EDS ( XN270325V1042 )匯入後, PDO Mapping 列表為空 | XAVIERA.FAN 范珮欣 | Completed
|  | Rev1.14.0 DIADesigner | Task | 582568 | DIADesigner source code permission application from MDSBU 陳贊宇 | BORONG.CHEN 陳柏融 | Completed
| 2 hours | Designer Rev1.14.0 Sprint2 | Task | 582518 | [RD_DEV] 修正 Corner 下載管理員 IsCompiled 判定邏輯 | MILENA.CHEN 陳孟歆 | Completed
1 hour | 1 hour 36 mins | Rev1.14.0 DIADesigner | Task | 582453 | [RD_DEV] 修正建立上下載項目的最上層過濾條件 | ARCHIE.YANG 楊浩群 | Completed
8 hours | 8 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 582319 | [RD_DEV]DeviceEvent 寫錯導致 event 沒有觸發 | WILLIAM.HC.SHEN 沈桓慶 | Completed
1 hour | 48 mins | Rev1.14.0 DIADesigner | Task | 582291 | [RD_DEV] VFD Monitor Table 釋放時需先關閉頁籤再釋放底層物件 | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 582229 | [RD_DEV] AS300EC 與 DVP-SEC 要處理 ECAT 與 IO 映射連動 | WILLIAM.HC.SHEN 沈桓慶 | Completed
30 mins | 12 mins | Designer Rev1.14.0 Sprint3 | Task | 582128 | [RD_DEV] 支援ASD A3-EX功能_DDF Model 新增，Port-X > Item-X 新增 ProtocolType HLLT | ARCHIE.YANG 楊浩群 | Completed
| 30 mins | Designer Rev1.14.0 Sprint3 | Task | 582127 | [RD_DEV] 支援ASD A3-EX功能_DDF 規格新增，Port-X > Item-X 新增 ProtocolType HLLT | MILENA.CHEN 陳孟歆 | Completed
| 36 mins | Designer Rev1.14.0 Sprint3 | Task | 581875 | [RD_DEV] 通訊設定: W3A 修改 DDF 中各通訊介面的預設站號 | MILENA.CHEN 陳孟歆 | Completed
| 4 hours | Designer Rev1.14.0 Sprint3 | Task | 581513 | [RD_DEV] 匯入 CANopen EDS 時, 從站識別資訊組成CANopen EDS 檔名需考量10進制與16進制轉換 | XAVIERA.FAN 范珮欣 | Completed
2 hours | 1 hour 30 mins | Rev1.14.0 DIADesigner | Task | 581412 | [RD_DEV] W3A 下載管理員內資料交換表與參數編輯器項目新增同步邏輯 | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 581324 | [RD_DEV] 驗證AS300EC 硬體配置通訊 | JEAN.LC.WANG 王儷臻 | Completed
4 hours |  | Designer Rev1.14.0 Sprint3 | Task | 581242 | [RD_DEV]EtherCAT ESI String Type 預設值為空值 | WILLIAM.HC.SHEN 沈桓慶 | Completed
| 3 hours 36 mins | Designer Rev1.14.0 Sprint3 | Task | 581144 | [RD_DEV](上載管理員) 裝置勾選三態修正 | JANET.JC.CHEN 陳美蓁 | Completed
| 10 hours 42 mins | Designer Rev1.14.0 Sprint3 | Task | 581137 | [RD_DEV] PLC 支援取消上載、下載並等待結束 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 42 mins | Rev1.14.0 DIADesigner | Task | 581118 | [RD_DEV] W3A 上下載管理員使用模擬器時禁止勾選參數編輯器項目 | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 581079 | [RD-DEV] [JIRA] (程式編輯) [IABGVOC-2013] 及時刷新 LOG 狀態下關閉頁籤，在线仿真發生例外 | KAKA.WU 吳思言 | Completed
8 hours | 6 hours | Designer Rev1.14.0 Sprint3 | Task | 581076 | [RD_DEV][W3A] 擴充 0x48 錯誤訊息多國語系 | JENNY.HY.CHEN 陳湘筠 | Completed
12 hours | 8 hours | Designer Rev1.14.0 Sprint3 | Task | 581075 | [RD_DEV][W3A] 擴充 0x48 sfc3 封包格式 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 8 hours 30 mins | Rev1.14.0 DIADesigner | Task | 580791 | [RD_DEV] (硬體配置) AS300EC 機種從硬體配置新增功能卡會出現Exception | NANCY.TC.YANG 楊采真 | Completed
| 4 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 580772 | [RD_DEV] AS332EC - NW支援雙網孔 | CLONE.LIN 林俊淵 | Completed
4 hours | 4 hours | Rev1.14.0 DIADesigner | Task | 580709 | [RD_DEV] Migrate DdfCheck from DIAOneWeb.WebAPI to DIADesigner | MILENA.CHEN 陳孟歆 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 580591 | (硬體配置) DVP16SEC裝置資訊例外 | JANET.JC.CHEN 陳美蓁 | Completed
|  | Rev1.14.0 DIADesigner | Task | 580454 | [RD_DEV](硬體配置) 取消轉送設定後開啟網路視圖參數設定被竄改 | NANCY.TC.YANG 楊采真 | Deferred
8 hours | 6 hours | Rev1.14.0 DIADesigner | Task | 580436 | [RD_DEV] (硬體配置) 取消轉送設定後開啟網路視圖參數設定被竄改 | NANCY.TC.YANG 楊采真 | Completed
2 hours | 1 hour 30 mins | Designer Rev1.14.0 Sprint2 | Task | 580409 | [RD_DEV] VFD CSV, XLSX 參數匯出不把空白的 Unit 輸出成 '#' | ARCHIE.YANG 楊浩群 | Completed
16 hours |  | Designer Rev1.14.0 Sprint2 | Task | 580402 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 Monitor 選項 | JOHNNY.MC.YEH 葉明勳 | Completed
16 hours |  | Designer Rev1.14.0 Sprint2 | Task | 580401 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 Adress 選項 | JOHNNY.MC.YEH 葉明勳 | Completed
16 hours |  | Designer Rev1.14.0 Sprint2 | Task | 580400 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 CANopen 選項 | JOHNNY.MC.YEH 葉明勳 | Completed
16 hours |  | Designer Rev1.14.0 Sprint2 | Task | 580235 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 Parameter 選項 | JOHNNY.MC.YEH 葉明勳 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 580022 | [RD_DEV] DVP16SV3_Online/Offline Status Bar | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 580015 | [RD_DEV] HMI 機種轉換 | JEAN.LC.WANG 王儷臻 | Completed
1 hour | 1 hour | Rev1.14.0 DIADesigner | Task | 579941 | [RD_DEV] 修正 DVP Scan 未還原整合 DIO 模組的問題 | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 579914 | [RD_DEV] 組態上載後更新實際值到輸入值欄位 | JEAN.LC.WANG 王儷臻 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 579812 | [RD_DEV] DVP 改用 ProdSubseries 判斷還原整合 DIO 模組 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 579798 | [RD_DEV] 修正 ASD 在上載管理員消失的問題 | ARCHIE.YANG 楊浩群 | Completed
| 9 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 579664 | [RD_DEV](上下載管理員) 父節點CheckStatus判斷修正、裝置節點預設Enable | JANET.JC.CHEN 陳美蓁 | Completed
| 2 hours 30 mins | Rev1.14.0 DIADesigner | Task | 579662 | [RD_DEV] 無裝置圖片時使用預設圖片 (ASD/HMI/VFD) | MILENA.CHEN 陳孟歆 | Completed
30 mins | 30 mins | Rev1.14.0 DIADesigner | Task | 579586 | [RD_DEV] W3A 連線時的驗證結果需保存 | ARCHIE.YANG 楊浩群 | Completed
24 hours | 10 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 579571 | [RD_DEV] W3A上載新增設備時, 須初始化 Embedded Device 通訊 | XAVIERA.FAN 范珮欣 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 579553 | [RD_DEV] APF3000_硬體配置通訊卡參數修正 | JANET.JC.CHEN 陳美蓁 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 579545 | [RD_DEV][W3A] 示波器簡化PLC位置不合法錯誤資訊 | JENNY.HY.CHEN 陳湘筠 | Completed
|  | Rev1.14.0 DIADesigner | Task | 579534 | DIADesigner source code permission application from MOK | BORONG.CHEN 陳柏融 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 579532 | [RD_DEV] HMI 存讀檔 | JEAN.LC.WANG 王儷臻 | Completed
1 hour | 27 mins | Designer Rev1.14.0 Sprint2 | Task | 579528 | [RD_DEV] 修正上載管理員內加入新裝置時沒有顯示節點 | ARCHIE.YANG 楊浩群 | Completed
| 2 hours 36 mins | Designer Rev1.14.0 Sprint2 | Task | 579524 | [RD_DEV] Corner 模擬器修改 Type 名稱 | XAVIERA.FAN 范珮欣 | Completed
1 hour | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 579337 | [RD_DEV] 新增 A3-EP 的 Device ID Code | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour 30 mins | Rev1.14.0 DIADesigner | Task | 579293 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Asd.*) | ARCHIE.YANG 楊浩群 | Completed
3 hours | 2 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 579204 | [RD_DEV] VFD: online 時, 狀態列顯示錯誤 | XAVIERA.FAN 范珮欣 | Completed
| 2 hours | Rev1.14.0 DIADesigner | Task | 579119 | [RD_DEV] 資料交換表顯示連線數 | FRANKNC.HO 何南瑾 | Completed
| 2 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 579040 | [RD_DEV]機種切換會發生例外 | JANET.JC.CHEN 陳美蓁 | Completed
30 mins | 48 mins | Rev1.14.0 DIADesigner | Task | 579026 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Corner.Communication) | ARCHIE.YANG 楊浩群 | Completed
| 30 mins | Designer Rev1.14.0 Sprint2 | Task | 578959 | [RD_DEV] AS332EC - 通訊: 設備無程式, 上載 Project CompactBin, 沒有上載結束事件 | XAVIERA.FAN 范珮欣 | Completed
2 hours | 2 hours | Rev1.14.0 DIADesigner | Task | 578957 | [RD_DEV] 修正寫 Device.xml Document NodeType 行為 | MILENA.CHEN 陳孟歆 | Completed
| 1 hour 30 mins | Designer Rev1.14.0 Sprint2 | Task | 578955 | [RD_DEV] AS332EC - 通訊: 特定韌體版本, 下載AppCompactBin 失敗 | XAVIERA.FAN 范珮欣 | Completed
| 4 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 578950 | [RD_DEV] TC 支援取消上載、下載並等待結束 | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 578934 | [RD_DEV](專案管理) [KA]硬件组态删除无法撤销；功能块或者程序块删除无法撤销 (改為跳提示訊息告知無法回復，且用戶可勾不再提示。) | JANET.JC.CHEN 陳美蓁 | Completed
4 hours | 3 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 578818 | [RD_DEV][JIRA] (專案管理) [IABGVOC-1786] DIADesigner专案名字有写小数点的版本号时，如果另外档案，目前会把最后一个小数点的数值删除掉 | NANCY.TC.YANG 楊采真 | Completed
8 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 578750 | [RD_DEV]支援ASD A3-EX功能 POC_DDF | MILENA.CHEN 陳孟歆 | In Progress
1 hour | 1 hour | Rev1.14.0 DIADesigner | Task | 578719 | [RD_DEV] 修正 TC 無法下載的問題 (Check 失敗) | ARCHIE.YANG 楊浩群 | Completed
| 5 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 578701 | [RD_DEV] ASD/Corner 支援取消上載、下載並等待結束 | ARCHIE.YANG 楊浩群 | Completed
3 hours | 5 hours | Rev1.14.0 DIADesigner | Task | 578693 | [RD_DEV] 改善上下載管理員效能 (ASD、VFD 有大量參數節點時) | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 578419 | [RD_DEV][W3A] HW_Tag_Table 新增按鈕更新以DDF內容為主產生系統變數的功能 | JEAN.LC.WANG 王儷臻 | Completed
4 hours | 5 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 578350 | [RD_DEV]支援ASD A3-EX功能 POC_Online/Offline_SRS | NANCY.TC.YANG 楊采真 | Completed
| 1 hour | Rev1.14.0 DIADesigner | Task | 578277 | [PLM] PJ126A-25D301 - 3-2-05_SE_SRS (Software) (3-2 SRS(Software)) | MILENA.CHEN 陳孟歆 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 578273 | [PLM] PJ134A-26-SS3-3-2-05_SE_SRS (Software) (3-2 SRS(Software)) | JEAN.LC.WANG 王儷臻 | Completed
2 hours | 3 hours | Designer Rev1.14.0 Sprint2 | Task | 578176 | [RD_DEV][W3A] 使用 W3A 模擬器連線示波器的情況下，監控項目若有 Servo Normal 則要跳警告視窗 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 578175 | [RD_DEV][W3A] 示波器監測項目為零的警告視窗增加易讀描述 | JENNY.HY.CHEN 陳湘筠 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 578174 | [RD_DEV][W3A] 進入多頻道模式時，應禁用各自座標系 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 578171 | [RD_DEV][W3A] 多通道示波器監控時，多通道 Y 軸沒有自動調整範圍 | JENNY.HY.CHEN 陳湘筠 | Completed
12 hours | 11 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 578140 | [RD_DEV]支援ASD A3-EX功能 POC_DI DO function configuration Requirement_SRS | NANCY.TC.YANG 楊采真 | Resolved
24 hours |  | Designer Rev1.14.0 Sprint2 | Task | 578133 | [RD_DEV] AS332EC - 下載管理員: 下載 App Compact Bin 修改觸發時間點 | JOHNNY.MC.YEH 葉明勳 | In Progress
1 hour | 1 hour 42 mins | Rev1.14.0 DIADesigner | Task | 578123 | [RD_DEV](線上模式) 線上模式匹配不符時， 英文的提示字會被切掉 | NANCY.TC.YANG 楊采真 | Completed
4 hours | 2 hours 9 mins | Rev1.14.0 DIADesigner | Task | 578070 | [RD_DEV](新增裝置) When clicking a node in the project tree with the mouse, the focused item does not display a colored background. (3/3) | NANCY.TC.YANG 楊采真 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 578013 | [RD_DEV][W3A] IOMap Subitem 的變數位址調整 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 578011 | RD/TE--軟體架構圖更新--同步DDF & DLL給DIASelector | JEAN.LC.WANG 王儷臻 | Completed
8 hours | 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577958 | [RD_DEV]支援ASD A3-EX功能 POC_Ethernet Connection Requirement_SRS | NANCY.TC.YANG 楊采真 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 577931 | [RD_DEV] HMI 專案樹節點右鍵開啟DIAScreen | JEAN.LC.WANG 王儷臻 | Completed
| 4 hours | Designer Rev1.14.0 Sprint3 | Task | 577848 | [RD_DEV]Form InitCmd 建立與預設參數相同的項目時，建立方式錯誤 | WILLIAM.HC.SHEN 沈桓慶 | Completed
4 hours | 4 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 577777 | [RD_DEV](網路配置) 项目树与网络视图控制，联动，可同时选中 | NANCY.TC.YANG 楊采真 | Completed
30 mins | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577624 | [RD_DEV] DVP16SV3_機種轉換 | NANCY.TC.YANG 楊采真 | Completed
4 hours | 4 hours | Designer Rev1.14.0 Sprint3 | Task | 577623 | [RD_DEV] DVP16SV3_示波器 | JOHNNY.MC.YEH 葉明勳 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 577622 | [RD_DEV] DVP16SV3_網路視圖 | FRANKNC.HO 何南瑾 | Assigned
8 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577620 | [RD_DEV] DVP16SV3_裝置與錯誤資訊 | MILENA.CHEN 陳孟歆 | Completed
2 hours | 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577619 | [RD_DEV] DVP16SV3_參數編輯器 | NANCY.TC.YANG 楊采真 | Completed
| 1 hour | Designer Rev1.14.0 Sprint3 | Task | 577618 | [RD_DEV] DVP16SV3_硬體配置 | JANET.JC.CHEN 陳美蓁 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 577617 | [RD_DEV] DVP16SV3_通訊設定 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 577616 | [RD_DEV] DVP16SV3_新增裝置 | JEAN.LC.WANG 王儷臻 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 577486 | [RD_DEV] APF3000_示波器 (離線功能) | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 2 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 577484 | [RD_DEV] APF3000_網路視圖 (離線功能) | CLONE.LIN 林俊淵 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 577482 | [RD_DEV] APF3000_裝置與錯誤資訊 (離線功能) | MILENA.CHEN 陳孟歆 | Completed
| 30 mins | Designer Rev1.14.0 Sprint2 | Task | 577479 | [RD_DEV] APF3000_硬體配置 (離線功能) | JANET.JC.CHEN 陳美蓁 | Completed
| 7 hours | Designer Rev1.14.0 Plan | Task | 577477 | [RD_DEV](下載管理員)EtherCAT、軸、E-CAM勾選連動與勾選三態修正 | JANET.JC.CHEN 陳美蓁 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 577473 | [RD_DEV] VA3000_示波器 (離線功能) | JENNY.HY.CHEN 陳湘筠 | Completed
| 1 hour 30 mins | Designer Rev1.14.0 Sprint2 | Task | 577472 | [RD_DEV] VA3000_網路視圖 (離線功能) | CLONE.LIN 林俊淵 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 577471 | [RD_DEV] VA3000_裝置與錯誤資訊 (離線功能) | MILENA.CHEN 陳孟歆 | Completed
| 2 hours | Designer Rev1.14.0 Sprint2 | Task | 577469 | [RD_DEV] VA3000_硬體配置 (離線功能) | JANET.JC.CHEN 陳美蓁 | Completed
| 2 hours | Designer Rev1.14.0 Sprint2 | Task | 577405 | [RD_DEV] W3A IQM Modbus Mapping_下載前編譯檢查 | MILENA.CHEN 陳孟歆 | Completed
| 6 mins | Designer Rev1.14.0 Sprint2 | Task | 577357 | [RD_DEV][W3A]若存檔格式有調整舊軟體不能開新版存檔內容 | JEAN.LC.WANG 王儷臻 | Resolved
1 hour | 30 mins | Rev1.14.0 DIADesigner | Task | 577354 | [RD_DEV] 修正 SetupDiGetClassDevs 回傳值的判斷方式 | ARCHIE.YANG 楊浩群 | Completed
| 6 hours | Designer Rev1.14.0 Sprint2 | Task | 577284 | [RD_DEV] 調整 Device Import 選擇資料夾 UI | MILENA.CHEN 陳孟歆 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 577179 | [RD_DEV]Corner 通訊 dll 和 ECAT 解耦 | WILLIAM.HC.SHEN 沈桓慶 | Completed
1 hour | 42 mins | Rev1.14.0 DIADesigner | Task | 577139 | [RD_DEV] 支援無配置時以預設行為初始化 CommgrHelper | ARCHIE.YANG 楊浩群 | Completed
1 hour | 42 mins | Rev1.14.0 DIADesigner | Task | 577137 | [RD_DEV] 修正判斷 ASDASoft Process 的邏輯，避免問錯對象，反覆發生例外 | ARCHIE.YANG 楊浩群 | Completed
40 hours |  | Designer Rev1.14.0 Sprint3 | Task | 577108 | [RD_DEV] 研究Black Duck工具與分析掃描報告 | JANET.JC.CHEN 陳美蓁 | In Progress
6 hours | 8 hours | Rev1.14.0 DIADesigner | Task | 577088 | [RD_DEV] W3A 增加 Servo 參數編輯器與上下載項目 | ARCHIE.YANG 楊浩群 | Completed
16 hours | 16 hours | Designer Rev1.14.0 Sprint2 | Task | 577069 | [RD_DEV] (網路配置)网络视图，拖拽链接时，不应该自动修改通讯地址，建议增加跳转可编辑选项 | CLONE.LIN 林俊淵 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Sprint2 | Task | 577005 | [RD_DEV]W3A EtherCAT 拓樸圖從站 Advance Option 禁用 revision 檢查 | WILLIAM.HC.SHEN 沈桓慶 | Completed
16 hours | 14 hours | Designer Rev1.14.0 Sprint2 | Task | 577004 | [RD_DEV]ECAT PDO配置UI優化 (新增PDO, 清單畫面不要跳至第一項/ 新增PDO參數做標示) | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours |  | Designer Rev1.14.0 Sprint2 | Task | 577001 | [RD_DEV]排除 W3A EtherCAT 停用導致編譯卡住的問題 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours |  | Designer Rev1.14.0 Sprint2 | Task | 576999 | [RD_DEV]修改 EtherCAT 專案，儲存使用的檔案名稱 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 10 hours | Designer Rev1.14.0 Sprint2 | Task | 576998 | [RD_DEV]ECAT從站客製化名稱要同步到軸上 | WILLIAM.HC.SHEN 沈桓慶 | Completed
16 hours | 28 hours | Designer Rev1.14.0 Sprint2 | Task | 576996 | [RD_DEV] EtherCAT ToolBar 添加 datagram 使用量 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Sprint2 | Task | 576994 | [RD_DEV]修改 ECAT 站號排列規則，從1001起 | WILLIAM.HC.SHEN 沈桓慶 | Completed
4 hours |  | Designer Rev1.14.0 Sprint2 | Task | 576993 | [RD_DEV]W3A ECAT 存檔造成到 Primary Task 間隔時間被改成 2ms | WILLIAM.HC.SHEN 沈桓慶 | Completed
24 hours |  | Designer Rev1.14.0 Sprint2 | Task | 576932 | [RD_DEV] AS332EC - 下載管理員: 下載 App Compact Bin 時, 須帶入 Program Checksum | JOHNNY.MC.YEH 葉明勳 | Completed
8 hours | 8 hours 12 mins | Designer Rev1.14.0 Sprint2 | Task | 576903 | [RD_DEV](專案管理) 當任一裝置切換成線上模式時，DIADesigner 應一律禁止上載下載行為 | NANCY.TC.YANG 楊采真 | Completed
| 2 hours | Designer Rev1.14.0 Sprint1 | Task | 576891 | [RD_DEV] Modbus Address Mapping 編譯錯誤後點擊錯誤訊息跳轉到對應畫面 | MILENA.CHEN 陳孟歆 | Completed
|  | Designer Rev1.14.0 Sprint1 | Task | 576859 | [RD_DEV] DVP 三代機 正確新增左右側模組 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 576791 | (專案管理) 主工具列新增自定義喜好按钮 (規格文件) | KAKA.WU 吳思言 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 576777 | 在DIADesigner的拓樸圖可加入HMI (的圖示)，用於專案前期對客戶說明規畫 (規格文件) | JEAN.LC.WANG 王儷臻 | Completed
2 hours | 2 hours | Designer Rev1.14.0 Sprint1 | Task | 576755 | [RD_DEV] 示波器停用動畫功能以提升效能，減少不必要運算 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours |  | Designer Rev1.14.0 Sprint2 | Task | 576749 | [RD_DEV] ASD 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 576748 | [RD_DEV] PLC logger & Tracer 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 10 hours | Designer Rev1.14.0 Sprint2 | Task | 576747 | [RD_DEV][W3A] W3A 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 576746 | [RD_DEV] VFD 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 576740 | [RD_DEV][W3A] 多畫布加入 visibleRange 變更事件 | JENNY.HY.CHEN 陳湘筠 | Completed
|  | Designer Rev1.14.0 Sprint1 | Task | 576618 | [RD_DEV] DVP 三代機模擬器連線 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint1 | Task | 576598 | [RD_DEV] DVP 三代機模組清單 | JEAN.LC.WANG 王儷臻 | Completed
| 1 hour | Designer Rev1.14.0 Sprint1 | Task | 576561 | [RD_DEV] CANopen 上載還原, 誤覆蓋 NW 中的 CANopen 主站 | XAVIERA.FAN 范珮欣 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Sprint3 | Task | 576491 | [RD_DEV][W3A] EtherCAT IO 映射表提供 sub channel 資訊給編譯器 | WILLIAM.HC.SHEN 沈桓慶 | Completed
| 1 hour | Designer Rev1.14.0 Sprint3 | Task | 576490 | [RD_DEV][W3A] Local IO 映射表提供 sub channel 資訊給編譯器 | JEAN.LC.WANG 王儷臻 | Completed
| 1 hour | Designer Rev1.14.0 Sprint3 | Task | 576489 | [RD_DEV][W3A] Motion interface IO 映射表提供 sub channel 資訊給編譯器 | JEAN.LC.WANG 王儷臻 | Completed
12 hours | 12 hours | Designer Rev1.14.0 Sprint2 | Task | 576481 | [RD_DEV]新增台達裝置從裝置樹批次添加功能 | WILLIAM.HC.SHEN 沈桓慶 | Completed
12 hours | 12 hours | Designer Rev1.14.0 Sprint2 | Task | 576480 | [RD_DEV]新增總線裝置批次添加功能 | WILLIAM.HC.SHEN 沈桓慶 | Completed
|  | Rev1.14.0 DIADesigner | Task | 576410 | [RD_DEV]匯出 | FRANKNC.HO 何南瑾 | Completed
4 hours | 4 hours | Rev1.14.0 DIADesigner | Task | 576409 | [RD_DEV]匯入不支援的Modbustcp版本或是不相同的Field Bus要防呆 | FRANKNC.HO 何南瑾 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 576375 | [RD_DEV] MX300 DDF Update to V1.03 (更新版本) | MILENA.CHEN 陳孟歆 | Completed
2 hours | 2 hours | Rev1.14.0 DIADesigner | Task | 576366 | [RD_DEV] 刪除 ASD 裝置時應正確釋放參數編輯器 | ARCHIE.YANG 楊浩群 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 576346 | [RD_DEV] ASD A3-M 新增 DDF (新機種) | MILENA.CHEN 陳孟歆 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 576345 | [RD_DEV] ASD B3-M 新增 DDF (新機種) | MILENA.CHEN 陳孟歆 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 576331 | [RD_DEV] ASD-A3-M 220V DDF Update (無版本更新) | MILENA.CHEN 陳孟歆 | Completed
| 1 hour | Designer Rev1.14.0 Plan | Task | 576260 | [RD_DEV] ASD-B3-M 220V DDF Update (無版本更新) | MILENA.CHEN 陳孟歆 | Completed
| 2 hours | Rev1.14.0 DIADesigner | Task | 576256 | (Cyber Security) Document clarify - Main Process | MILENA.CHEN 陳孟歆 | Completed
32 hours | 17 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 576235 | [RD_DEV]DURApulse Designer 2st Beta SW Review Reply_20260413 | NANCY.TC.YANG 楊采真 | Completed
24 hours | 18 hours | Designer Rev1.14.0 Sprint3 | Task | 576071 | [RD_DEV] 規劃如何讓Security Main Process運行在既有Designer版本流程上 | NANCY.TC.YANG 楊采真 | In Progress
| 2 hours 6 mins | Designer Rev1.14.0 Plan | Task | 576020 | [RD_DEV](專案管理) AS 機種專案下載節點訊息顯示內容不符預期 | JANET.JC.CHEN 陳美蓁 | Completed
1 hour | 1 hour 30 mins | Rev1.14.0 DIADesigner | Task | 576006 | [RD_DEV] 調整 MODBUS 接收資料的預設 Delay 為 0 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 575993 | (Cyber Security) Regular review process of Main Process | CLONE.LIN 林俊淵 | Completed
| 3 hours 36 mins | Designer Rev1.14.0 Sprint2 | Task | 575926 | [RD_DEV] VFD 支援取消上載、下載並等待結束 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 575864 | (Cyber Security) Regular review process of General Review Process | CLONE.LIN 林俊淵 | Completed
8 hours | 2 hours | Designer Rev1.14.0 Plan | Task | 575846 | [RD_DEV][W3A] 示波器增加最小、最大、平均值顯示欄位 | JENNY.HY.CHEN 陳湘筠 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 575782 | [RD_DEV]DURApulse Designer 2st Beta SW Review Reply_20260409 | NANCY.TC.YANG 楊采真 | Completed
24 hours | 10 hours | Designer Rev1.14.0 Sprint3 | Task | 575705 | (Cyber Security) Regular review process of TMRA Process | JANET.JC.CHEN 陳美蓁 | Completed
8 hours |  | Designer Rev1.14.0 Sprint2 | Task | 575269 | [RD_DEV] ASD_DLL權限申請與驗證 | JOHNNY.MC.YEH 葉明勳 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 575221 | [RD_DEV] DVPSEC - 通訊: 上載 App Compact Bin, 固化方案版號, Program Checksum | XAVIERA.FAN 范珮欣 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint2 | Task | 575219 | [RD_DEV] DVPSEC - 通訊: 下載 Program Checksum 與 固化方案版號 | XAVIERA.FAN 范珮欣 | Completed
40 hours |  | Designer Rev1.14.0 Sprint2 | Task | 575205 | [RD_DEV](B5 Oscilloscope)ASD_DLL COM Port API串接 | JOHNNY.MC.YEH 葉明勳 | Assigned
24 hours |  | Designer Rev1.14.0 Sprint2 | Task | 575198 | [RD_DEV] B5 專案下載韌體除錯 | JOHNNY.MC.YEH 葉明勳 | Completed
8 hours |  | Rev1.14.0 DIADesigner | Task | 575176 | [RD_DEV] DVPSEC - 上載管理員: 觸發上載 App Compact Bin | JOHNNY.MC.YEH 葉明勳 | Completed
24 hours |  | Designer Rev1.14.0 Sprint2 | Task | 575175 | [RD_DEV] AS332EC -上載管理員: 觸發上載 App Compact Bin | JOHNNY.MC.YEH 葉明勳 | Completed
|  | Rev1.14.0 DIADesigner | Task | 575138 | [RD_DEV]匯入 | FRANKNC.HO 何南瑾 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 575111 | [RD_DEV] CANopen 掃描結果: Unknwon Device 呈現於掃描結果列表 | FRANKNC.HO 何南瑾 | Completed
8 hours | 3 hours | Designer Rev1.14.0 Sprint3 | Task | 575110 | [RD_DEV] CANopen 掃描通訊: 提供 Unknown Device 的識別資訊 | XAVIERA.FAN 范珮欣 | Completed
| 9 hours 6 mins | Designer Rev1.14.0 Sprint1 | Task | 575089 | [RD_DEV](硬體配置) DVP16SEC上載管理員配置出現錯誤子項目 | JANET.JC.CHEN 陳美蓁 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 574840 | [RD_DEV] MA500_通訊測試工具 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 574839 | [RD_DEV] MA500_示波器 | JENNY.HY.CHEN 陳湘筠 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 574838 | [RD_DEV] MA500_數位操作器 | JENNY.HY.CHEN 陳湘筠 | Completed
1 hour |  | Designer Rev1.14.0 Sprint3 | Task | 574837 | [RD_DEV] MA500_網路視圖 | CLONE.LIN 林俊淵 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 574836 | [RD_DEV] MA500_裝置與錯誤資訊 | MILENA.CHEN 陳孟歆 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 574835 | [RD_DEV] MA500_上下載 | JANET.JC.CHEN 陳美蓁 | Completed
8 hours | 2 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574834 | [RD_DEV] MA500_參數編輯器 | NANCY.TC.YANG 楊采真 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 574833 | [RD_DEV] MA500_硬體配置 | JANET.JC.CHEN 陳美蓁 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574832 | [RD_DEV] MA500_通訊設定 | XAVIERA.FAN 范珮欣 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574831 | [RD_DEV] MA500_變頻精靈 | XAVIERA.FAN 范珮欣 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 574830 | [RD_DEV] MA500_新增裝置 | MILENA.CHEN 陳孟歆 | Completed
8 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 574829 | [RD_DEV] MA500_DDF (新機種) | MILENA.CHEN 陳孟歆 | Completed
4 hours |  | Designer Rev1.14.0 Sprint3 | Task | 574826 | [RD_DEV] APF3000_通訊測試工具 | JENNY.HY.CHEN 陳湘筠 | Assigned
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 574823 | [RD_DEV] APF3000_示波器 | JENNY.HY.CHEN 陳湘筠 | Assigned
4 hours |  | Designer Rev1.14.0 Sprint3 | Task | 574822 | [RD_DEV] APF3000_數位操作器 | JENNY.HY.CHEN 陳湘筠 | Assigned
|  | Designer Rev1.14.0 Sprint3 | Task | 574821 | [RD_DEV] APF3000_網路視圖 | CLONE.LIN 林俊淵 | Assigned
|  | Designer Rev1.14.0 Sprint3 | Task | 574819 | [RD_DEV] APF3000_上下載 | JANET.JC.CHEN 陳美蓁 | Assigned
|  | Designer Rev1.14.0 Sprint3 | Task | 574817 | [RD_DEV] APF3000_硬體配置 | JANET.JC.CHEN 陳美蓁 | Assigned
4 hours |  | Designer Rev1.14.0 Sprint3 | Task | 574816 | [RD_DEV] APF3000_通訊設定 | XAVIERA.FAN 范珮欣 | Assigned
4 hours |  | Designer Rev1.14.0 Sprint3 | Task | 574815 | [RD_DEV] APF3000_變頻精靈 | XAVIERA.FAN 范珮欣 | Assigned
4 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 574813 | [RD_DEV] APF3000_新增裝置 & DDF/EDS (release 前移除) | MILENA.CHEN 陳孟歆 | Completed
4 hours |  | Rev1.14.0 DIADesigner | Task | 574793 | [RD_DEV]更新多國語系_1.14.0 | KAKA.WU 吳思言 | Assigned
2 hours | 1 hour | Designer Rev1.14.0 Sprint1 | Task | 574786 | [RD_DEV] MX300-S_新增裝置 & DDF (新機種) | MILENA.CHEN 陳孟歆 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Plan | Task | 574667 | [RD_DEV] EtherCAT_Tag_Table 變數名稱異常 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 1 hour 36 mins | Designer Rev1.14.0 Sprint2 | Task | 574659 | [RD_DEV] AS332EC - 通訊: 取得 Program Checksum 與 固化方案版號 | XAVIERA.FAN 范珮欣 | Completed
12 hours | 6 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 574652 | [RD_DEV] AS332EC - 通訊: 下載 固化方案版號 與 Program Checksum | XAVIERA.FAN 范珮欣 | Completed
24 hours | 5 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 574651 | [RD_DEV] AS332EC - 通訊: 上載 App Compact Bin | XAVIERA.FAN 范珮欣 | Completed
24 hours |  | Designer Rev1.14.0 Sprint1 | Task | 574225 | [RD_DEV] W3A 多節點示波器 - Pool - 建立資料池 | JOHNNY.MC.YEH 葉明勳 | Completed
40 hours |  | Designer Rev1.14.0 Plan | Task | 574224 | [RD_DEV] W3A 多節點示波器 - Pool (1.14) | JOHNNY.MC.YEH 葉明勳 | Completed
|  | Designer Rev1.14.0 Plan | Task | 574221 | [RD_DEV] W3A 多節點示波器 (1.14) | JENNY.HY.CHEN 陳湘筠 | Assigned
| 2 hours | Designer Rev1.14.0 Sprint1 | Task | 574070 | [RD_DEV]排除 B5 EtherCAT 下載遇到問題 | WILLIAM.HC.SHEN 沈桓慶 | Completed
1 hour | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574005 | [RD_DEV] 通訊設定: 驗證 W3A 預設站號為 200 | XAVIERA.FAN 范珮欣 | Completed
24 hours | 8 hours | Designer Rev1.14.0 Sprint3 | Task | 574003 | [RD_DEV] 通訊設定: 預設站號從 DDF 取得 | XAVIERA.FAN 范珮欣 | Completed
8 hours | 9 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 573572 | [RD_DEV] HMI 圖檔 | MILENA.CHEN 陳孟歆 | Completed
16 hours | 9 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 573571 | [RD_DEV] HMI NW | CLONE.LIN 林俊淵 | Completed
| 6 mins | Designer Rev1.14.0 Sprint2 | Task | 573569 | [RD_DEV] HMI在軟體上工具列上通用功能的皆須防呆不可操作 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 573567 | [RD_DEV] 新增 HMI 機種 | JEAN.LC.WANG 王儷臻 | Completed
| 1 hour | Designer Rev1.14.0 Sprint2 | Task | 573565 | [RD_DEV] 確認支援HMI機種與DDF (無版本更新) | MILENA.CHEN 陳孟歆 | Completed
| 9 hours | Rev1.14.0 DIADesigner | Task | 573547 | [RD_DEV] IABG Specification_DIADesigner 功能總表進版 | MILENA.CHEN 陳孟歆 | Completed
| 8 hours | Rev1.14.0 DIADesigner | Task | 573433 | [RD_DEV] IABG Specification_DDF Spec 轉移成 Confluence Page | MILENA.CHEN 陳孟歆 | Completed
| 2 hours 12 mins | Designer Rev1.14.0 Sprint3 | Task | 573304 | [RD_DEV] DVPSEC - 驗證 硬體配置連線功能 | JEAN.LC.WANG 王儷臻 | In Progress
| 7 hours | Designer Rev1.14.0 Sprint3 | Task | 573099 | (Cyber Security) Regular review process of Configuration Items | JANET.JC.CHEN 陳美蓁 | Completed
|  | Rev1.14.0 DIADesigner | Task | 573068 | [RD_DEV] 架構圖更新 (Commission part) - DIADesigner v1.14.0 | ARCHIE.YANG 楊浩群 | Assigned
|  | Rev1.14.0 DIADesigner | Task | 573067 | [RD_DEV] 架構圖更新 (UI part) - DIADesigner v1.14.0 | KAKA.WU 吳思言 | Assigned
|  | Rev1.14.0 DIADesigner | Task | 573066 | [RD_DEV] 架構圖更新 (Oscilloscope part) - DIADesigner v1.14.0 | JENNY.HY.CHEN 陳湘筠 | Assigned
|  | Rev1.14.0 DIADesigner | Task | 573065 | [RD_DEV] 架構圖更新 (Communication part) - DIADesigner v1.14.0 | XAVIERA.FAN 范珮欣 | Assigned
|  | Rev1.14.0 DIADesigner | Task | 573064 | [RD_DEV] 架構圖更新 (NW part) - DIADesigner v1.14.0 | CLONE.LIN 林俊淵 | Assigned
|  | Rev1.14.0 DIADesigner | Task | 573063 | [RD_DEV] 架構圖更新 (HW part) - DIADesigner v1.14.0 | ARCHIE.YANG 楊浩群 | Assigned
| 2 hours | Designer Rev1.14.0 Sprint1 | Task | 572907 | [PLM] PJ116A-MS300-NEMA4X-DB, PJ116A-MS300-NEMA4X-D - 3-2-05_SE_SRS (Software) (3-2 SRS(Software)) | JEAN.LC.WANG 王儷臻 | Completed
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 572839 | [RD_DEV] AS332EC - 設備主體: 上載管理員 - 上載 Project Compact Bin 前, 取消比對 Checksum | JOHNNY.MC.YEH 葉明勳 | Completed
16 hours | 2 hours | Designer Rev1.14.0 Sprint1 | Task | 572752 | [RD_DEV] 初步驗證 B5 下載 | JEAN.LC.WANG 王儷臻 | In Progress
|  | Rev1.14.0 DIADesigner | Task | 572578 | Project Summary: DIADesigner Rev1.14.0 | BORONG.CHEN 陳柏融 | In Progress
40 hours | 20 hours | Rev1.14.0 DIADesigner | Task | 572194 | [RD_DEV] 1.14.0 PJM & PMO Related work | NANCY.TC.YANG 楊采真 | In Progress
| 1 hour 30 mins | Designer Rev1.14.0 Sprint2 | Task | 572033 | [RD_DEV][W3A] RefreshIndexTool Corner Mode | JEAN.LC.WANG 王儷臻 | Completed
1 hour |  | Rev1.14.0 DIADesigner | Task | 571837 | [RD_DEV] DDF & EDS index files version refresh (for DIADesigner 1.14.0) | MILENA.CHEN 陳孟歆 | Assigned
16 hours | 6 hours | Designer Rev1.14.0 Plan | Task | 570316 | [RD_DEV][W3A] 示波器停止時最小、最大、平均值隨畫面範圍內的數值變化 | JENNY.HY.CHEN 陳湘筠 | Completed
3 hours | 3 hours | Designer Rev1.14.0 Sprint3 | Task | 569952 | [RD_DEV] DVP16SV3 HW存讀檔需容舊型號 | ARCHIE.YANG 楊浩群 | Completed
|  | Designer Rev1.14.0 Sprint1 | Task | 569945 | [RD_DEV] DVP16SV3 機種變更清單 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint3 | Task | 569944 | [RD_DEV] 更新 DVP 更換系列的DDF (調整系列名) | MILENA.CHEN 陳孟歆 | In Progress
|  | Designer Rev1.14.0 Sprint2 | Task | 569336 | [RD_DEV] (新增裝置)(工程版)支援ASD-B5 - 規格文件 | JEAN.LC.WANG 王儷臻 | Assigned
|  | Designer Rev1.14.0 Sprint3 | Task | 569004 | [RD_DEV] DVPSEC - 設備主體: 上載管理員: EtherCAT節點Checksum與設備上載回的Checksum不一致 | WILLIAM.HC.SHEN 沈桓慶 | Completed
| 5 hours | Designer Rev1.14.0 Sprint1 | Task | 568350 | [RD_DEV] AS332EC - Survey: 上載後可直接Online 不須新編譯, 通訊需求討論 | XAVIERA.FAN 范珮欣 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 566580 | [RD_DEV] 組態上載 封包間間隔時間略長 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 566578 | [RD_DEV] 詢問是否上載子選單細項內容 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint1 | Task | 566576 | [RD_DEV] 支援 MX 逆變軸組態上載 | JEAN.LC.WANG 王儷臻 | Completed
| 12 mins | Designer Rev1.14.0 Sprint1 | Task | 566575 | [RD_DEV]支援 MX 整流組態上載 | JEAN.LC.WANG 王儷臻 | Completed
| 3 hours 12 mins | Designer Rev1.14.0 Sprint1 | Task | 565887 | [RD_DEV] 支援 GV50的Eth組態上載 | JEAN.LC.WANG 王儷臻 | Completed
|  | Rev1.14.0 DIADesigner | Task | 565510 | VFD MNTR 示波器及組態上載規格整理(serial, ethernet) | JOHNNY.MC.YEH 葉明勳 | Completed
|  | Designer Rev1.14.0 Sprint1 | Task | 565106 | [RD_DEV] VP-E/EHS 支援組態上載前的語系切換功能 | JEAN.LC.WANG 王儷臻 | In Progress
|  | Designer Rev1.14.0 Sprint2 | Task | 565103 | [RD_DEV] VP-E/EHS 高速組態上載 | JEAN.LC.WANG 王儷臻 | Assigned
24 hours | 12 hours | Designer Rev1.14.0 Plan | Task | 564806 | [RD_DEV]當使用者配置的 EtherCAT 從站項目，有超出 FECAT 或 DVP-ES3(TEC) 限制的 pdo entry數量時，跳出警告 | WILLIAM.HC.SHEN 沈桓慶 | In Progress
5 hours |  | Designer Rev1.14.0 Plan | Task | 562193 | [RD_DEV] 當移除 DVP-EN02 配置時，轉換前需提示訊息，告知 DVP-EN02 配置及相關資料交換將被刪除 | JANET.JC.CHEN 陳美蓁 | Assigned
5 hours |  | Designer Rev1.14.0 Plan | Task | 562192 | [RD_DEV] 當移除 EIP RTU 配置時，轉換前需提示訊息，告知 RTU 配置及相關資料交換將被刪除 | JANET.JC.CHEN 陳美蓁 | Assigned
4 hours |  | Designer Rev1.14.0 Plan | Task | 562191 | [RD_DEV] 若轉換成 AS300 系列，且有配置 EtherCAT 時，需自動配置 AS-FECAT 卡 | WILLIAM.HC.SHEN 沈桓慶 | Assigned
16 hours |  | Designer Rev1.14.0 Plan | Task | 562190 | [RD_DEV] 若轉換成 AS300 系列，且有配置 CANopen 時，需自動配置 AS-FCOPM 卡 | CLONE.LIN 林俊淵 | Assigned
4 hours |  | Designer Rev1.14.0 Plan | Task | 562188 | [RD_DEV] DVP-ES3(TEC) 機種轉換成 AS300 時，保留 EtherCAT 配置、EtherCAT IO 映射變數 | WILLIAM.HC.SHEN 沈桓慶 | Assigned
|  | Designer Rev1.14.0 Plan | Task | 562187 | [RD_DEV] 資料交換表的從站裝置支援上限檢查 (EIP, CANopen) | FRANKNC.HO 何南瑾 | Assigned
|  | Designer Rev1.14.0 Plan | Task | 562186 | [RD_DEV] 資料交換表的主站暫存器支援範圍檢查 (Modbus, ModbusTcp, EIP, CANopen) | FRANKNC.HO 何南瑾 | Assigned
16 hours |  | Designer Rev1.14.0 Plan | Task | 562185 | [RD_DEV] 通訊參數皆需保留 (Modbus, ModbusTcp, EIP, CANopen) | CLONE.LIN 林俊淵 | Assigned
|  | Designer Rev1.14.0 Sprint2 | Task | 562057 | [RD_DEV] AS332EC - ASDEV DDF 紀錄固化方案版本 | JEAN.LC.WANG 王儷臻 | Completed
|  | Rev1.14.0 DIADesigner | Task | 560174 | [RD_DEV] 修改VFD SRS Template內容 | NANCY.TC.YANG 楊采真 | In Progress
40 hours | 5 hours | Rev1.14.0 DIADesigner | Task | 560172 | [RD_DEV] 修改SAS內容 | NANCY.TC.YANG 楊采真 | Completed
16 hours | 12 hours | Rev1.14.0 DIADesigner | Task | 558807 | [RD_DEV] 申請表併入SAS、參數對應表、SRS等文件 | NANCY.TC.YANG 楊采真 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 552362 | [RD_DEV][W3A] HW裝置比對 | JEAN.LC.WANG 王儷臻 | Assigned
16 hours |  | Designer Rev1.14.0 Sprint3 | Task | 550865 | [RD_DEV][W3A] - 通訊: Online - 使用實機, 取得 ASD 設備狀態 | JEAN.LC.WANG 王儷臻 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 550860 | [RD_DEV][W3A] HW - Online前比對取得 Checksum, 使用 Corner Communication | JEAN.LC.WANG 王儷臻 | In Progress
16 hours |  | Designer Rev1.14.0 Sprint2 | Task | 549498 | [RD_DEV][W3A] update W3A DDF | JEAN.LC.WANG 王儷臻 | In Progress
|  | Designer Rev1.14.0 Sprint2 | Task | 546040 | [RD_DEV] IEC 62443-4-1 合規 (Part1)_Conformity of DM-1 | CLONE.LIN 林俊淵 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 546033 | (Cyber Security) Regular review process of Development Master Record | CLONE.LIN 林俊淵 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 546032 | (Cyber Security) Regular review process of SBOM Process | CLONE.LIN 林俊淵 | Completed
| 5 hours | Designer Rev1.14.0 Sprint2 | Task | 546029 | (Cyber Security) Regular review process of Single Develop Task Process | JANET.JC.CHEN 陳美蓁 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 546027 | [RD_DEV] IEC 62443-4-1 合規 (Part1)_DM checklist_Rational - Product Dashboard | BORONG.CHEN 陳柏融 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 546013 | [RD_DEV] IEC 62443-4-1 合規 (Part1)_TMRA Report (CSRS) | CLONE.LIN 林俊淵 | Completed
|  | Designer Rev1.14.0 Sprint2 | Task | 542232 | [RD_DEV] 支援 GV50的高速組態上載 | JEAN.LC.WANG 王儷臻 | In Progress
16 hours | 10 hours | Designer Rev1.14.0 Plan | Task | 540114 | [RD_DEV][W3A] 示波器導入VFD示波器的事件觸發功能 | JENNY.HY.CHEN 陳湘筠 | In Progress
8 hours | 15 mins | Rev1.14.0 DIADesigner | Task | 532083 | [RD_DEV] VFD_資料交換表文件範圍確認與更新 | NANCY.TC.YANG 楊采真 | Resolved
24 hours |  | Designer Rev1.14.0 Plan | Task | 528310 | [RD_DEV] 調機精靈_Development_示波器相關功能_波形存檔 | JENNY.HY.CHEN 陳湘筠 | In Progress
|  | Designer Rev1.14.0 Sprint2 | Task | 527352 | [RD_DEV][W3A] - Corner 參數編輯器 | JEAN.LC.WANG 王儷臻 | Assigned
|  | Designer Rev1.14.0 Sprint2 | Task | 527350 | [RD_DEV][W3A] - 伺服參數編輯器數值讀寫 | JEAN.LC.WANG 王儷臻 | Assigned
|  | Designer Rev1.14.0 Sprint2 | Task | 527347 | [RD_DEV][W3A] - 伺服參數編輯器 畫面與項目 | JEAN.LC.WANG 王儷臻 | Assigned
40 hours | 19 hours | Rev1.14.0 DIADesigner | Task | 527017 | [RD_DEV][W3A]通訊參數設定-下載通訊相關參數 | ARCHIE.YANG 楊浩群 | Completed
40 hours | 12 hours 6 mins | Rev1.14.0 DIADesigner | Task | 527016 | [RD_DEV][W3A]通訊參數設定-上載通訊相關參數 | ARCHIE.YANG 楊浩群 | Completed
4 hours | 4 hours | Designer Rev1.14.0 Sprint2 | Task | 526437 | [RD_DEV][W3A] Corner 示波器各CH獨立頻寬操作 - 配合機種DDF來呈現取樣頻率清單 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 525572 | [RD_DEV] AS332EC - 設備主體: Compact bin 改善File Size | XAVIERA.FAN 范珮欣 | Assigned
8 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 525431 | [RD_DEV][W3A] - 產品包驗證 | JEAN.LC.WANG 王儷臻 | In Progress
40 hours |  | Designer Rev1.14.0 Sprint2 | Task | 525174 | [RD_DEV] AS332EC - Embedded Corner: 固化方案 - 更新機制的相容性 | JEAN.LC.WANG 王儷臻 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 525119 | [RD_DEV] AS332EC - 設備主體: 無法執行 PLC EIP Scan 功能 | CLONE.LIN 林俊淵 | Completed
8 hours |  | Designer Rev1.14.0 Plan | Task | 524598 | [RD_DEV][W3A] EtherCAT 匯出 ENI（2026Q1） | WILLIAM.HC.SHEN 沈桓慶 | Assigned
4 hours | 2 hours 18 mins | Rev1.14.0 DIADesigner | Task | 523127 | [RD_DEV] VFD_裝置Online/Offline資訊文件範圍確認(Config) | NANCY.TC.YANG 楊采真 | Completed
40 hours | 1 hour | Rev1.14.0 DIADesigner | Task | 523123 | [RD_DEV] VFD_調適資訊文件範圍確認與更新_Config | NANCY.TC.YANG 楊采真 | Resolved
2 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 522702 | [RD_DEV] DVPSEC - Check NW PC Scan 是否可找到 DVPSEC | CLONE.LIN 林俊淵 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 522701 | [RD_DEV] DVPSEC - Check NW 是否可執行PLC EIP Scan功能 | CLONE.LIN 林俊淵 | Completed
8 hours | 6 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 521989 | [RD_DEV] DVPSEC - Embedded Corner下載管理員: Post Download | XAVIERA.FAN 范珮欣 | Resolved
4 hours |  | Designer Rev1.14.0 Sprint2 | Task | 521977 | [RD_DEV] DVPSEC - 設備能力透過外部檔案取得 | XAVIERA.FAN 范珮欣 | Assigned
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 521974 | [RD_DEV] DVPSEC - 模擬器不支援功能 | JOHNNY.MC.YEH 葉明勳 | Assigned
3 hours |  | Designer Rev1.14.0 Sprint3 | Task | 521973 | [RD_DEV] DVPSEC - 通訊 連線至模擬器 | XAVIERA.FAN 范珮欣 | Assigned
|  | Designer Rev1.14.0 Sprint3 | Task | 521971 | [RD_DEV] DVPSEC - ECAT: 驗證功能 | WILLIAM.HC.SHEN 沈桓慶 | Completed
16 hours |  | Designer Rev1.14.0 Sprint2 | Task | 521966 | [RD_DEV] DVPSEC - 產品包驗證 | JEAN.LC.WANG 王儷臻 | In Progress
1 hour |  | Designer Rev1.14.0 Plan | Task | 518208 | [RD_DEV] 其它-模擬器 | CLONE.LIN 林俊淵 | Completed
1 hour |  | Designer Rev1.14.0 Plan | Task | 518204 | [RD_DEV] 符號表-IO-Link Tag Table | FRANKNC.HO 何南瑾 | Completed
40 hours |  | Designer Rev1.14.0 Plan | Task | 518203 | [RD_DEV] 符號表-IO-Link I/O Mapping | FRANKNC.HO 何南瑾 | Rejected
0 hours | 0 hours | Designer Rev1.14.0 Plan | Task | 518202 | [RD_DEV] IO-Link Device 監控頁面 | CLONE.LIN 林俊淵 | Completed
16 hours | 16 hours 30 mins | Designer Rev1.14.0 Plan | Task | 518201 | [RD_DEV] IO-Link Master 監控頁面 | CLONE.LIN 林俊淵 | Completed
0 hours |  | Designer Rev1.14.0 Plan | Task | 518200 | [RD_DEV] IO-Link 監控頁面的主畫面 | CLONE.LIN 林俊淵 | Completed
0 hours |  | Designer Rev1.14.0 Plan | Task | 518199 | [RD_DEV] IO-Link 監控頁面 | CLONE.LIN 林俊淵 | Completed
0 hours | 0 hours | Designer Rev1.14.0 Plan | Task | 518198 | [RD_DEV] IO-Link Device 設定頁面 - Process Data 分頁 | FRANKNC.HO 何南瑾 | Completed
56 hours | 1 hour 18 mins | Designer Rev1.14.0 Plan | Task | 518197 | [RD_DEV] IO-Link Device 設定頁面 - Parameter 分頁 | KAKA.WU 吳思言 | Completed
32 hours | 24 hours | Designer Rev1.14.0 Plan | Task | 518196 | [RD_DEV] IO-Link Master 設定頁面 - Process Data 分頁 | CLONE.LIN 林俊淵 | Completed
16 hours |  | Designer Rev1.14.0 Plan | Task | 518186 | [RD_DEV] 全域工具列-監控 IO-Link 資訊 | CLONE.LIN 林俊淵 | Completed
16 hours | 4 hours 30 mins | Designer Rev1.14.0 Sprint1 | Task | 507752 | [RD_DEV] DIADesigner shall be able to download/upload via the AS-FFTP01 card | CLONE.LIN 林俊淵 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 507452 | [RD_DEV] AS332EC - 通訊: 連線至模擬器 | XAVIERA.FAN 范珮欣 | Assigned
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 507066 | [RD_DEV] AS332EC - 模擬器不支援功能 | JOHNNY.MC.YEH 葉明勳 | Assigned
24 hours |  | Designer Rev1.14.0 Sprint3 | Task | 505507 | [RD_DEV] AS332EC - 設備能力透過外部檔案取得 | XAVIERA.FAN 范珮欣 | Assigned
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 505453 | [RD_DEV] VA3000_通訊測試工具 | JENNY.HY.CHEN 陳湘筠 | Assigned
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 505451 | [RD_DEV] VA3000_示波器 | JENNY.HY.CHEN 陳湘筠 | Assigned
8 hours |  | Designer Rev1.14.0 Sprint3 | Task | 505449 | [RD_DEV] VA3000_數位操作器 | JENNY.HY.CHEN 陳湘筠 | Assigned
4 hours | 3 hours | Designer Rev1.14.0 Sprint2 | Task | 505435 | [RD_DEV] VA3000_新增裝置 & DDF (release 前移除) | MILENA.CHEN 陳孟歆 | Completed
24 hours |  | Rev1.14.0 DIADesigner | Task | 505160 | [RD_DEV] 調整 PLC 主機下載流程，優先下載 CANopen 參數，第一階段 | ARCHIE.YANG 楊浩群 | Assigned
24 hours |  | Rev1.14.0 DIADesigner | Task | 505153 | [RD_DEV] 從 Model 建立 PLC 參數，優化效能 | ARCHIE.YANG 楊浩群 | Assigned
16 hours | 14 hours | Designer Rev1.14.0 Sprint2 | Task | 499614 | [RD_DEV] AS332EC - Corner 產品包驗證 | JEAN.LC.WANG 王儷臻 | In Progress
24 hours | 2 hours | Rev1.14.0 DIADesigner | Task | 484525 | [RD_DEV] ADC客製案_Architecture Design_採用注入方式 | ARCHIE.YANG 楊浩群 | In Progress