## Sheet1
Estimate | TimeSpend | Planned For | Type | ID | Summary | Owner | State
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 583940 | [RD_DEV] 網路視圖在特定操作下刪除總線網路會發生線段殘留現象 | CLONE.LIN 林俊淵 | Completed
30 mins | 3 mins | Designer Rev1.14.0 Sprint3 | Task | 583575 | [RD_DEV] 新增 DIO 調機 Icon | ARCHIE.YANG 楊浩群 | Completed
1 hour | 24 mins | Designer Rev1.14.0 Sprint3 | Task | 583543 | [RD_DEV] 開啟通訊設定視窗時更新專案樹呈現的裝置連線狀況 | ARCHIE.YANG 楊浩群 | Completed
4 hours | 3 hours 18 mins | Designer Rev1.14.0 Sprint3 | Task | 583532 | [RD_DEV] 新增不做資料處理的 ModbusProtocolBase，新增可自訂 IConnector 的 Ethernet 設定物件 | ARCHIE.YANG 楊浩群 | Completed
2 hours | 1 hour 54 mins | Designer Rev1.14.0 Sprint3 | Task | 583509 | [RD_DEV] ETH 通訊設定改用統一的 Element Name 儲存 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 51 mins | Designer Rev1.14.0 Sprint3 | Task | 583499 | [RD_DEV] 調整 ASD Run/Stop 狀態訊息為 Servo On/Off | ARCHIE.YANG 楊浩群 | Completed
16 hours | 8 hours | Designer Rev1.14.0 Sprint3 | Task | 583237 | [RD_DEV]ECAT 掃描更新事件 | WILLIAM.HC.SHEN 沈桓慶 | Resolved
4 hours | 3 hours | Designer Rev1.14.0 Sprint2 | Task | 582732 | [RD_DEV] MX300 keypad 取值失敗時不應清空數值及單位 | JENNY.HY.CHEN 陳湘筠 | Completed
1 hour | 1 hour 36 mins | Rev1.14.0 DIADesigner | Task | 582453 | [RD_DEV] 修正建立上下載項目的最上層過濾條件 | ARCHIE.YANG 楊浩群 | Completed
8 hours | 8 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 582319 | [RD_DEV]DeviceEvent 寫錯導致 event 沒有觸發 | WILLIAM.HC.SHEN 沈桓慶 | Completed
1 hour | 48 mins | Rev1.14.0 DIADesigner | Task | 582291 | [RD_DEV] VFD Monitor Table 釋放時需先關閉頁籤再釋放底層物件 | ARCHIE.YANG 楊浩群 | Completed
30 mins | 12 mins | Designer Rev1.14.0 Sprint3 | Task | 582128 | [RD_DEV] 支援ASD A3-EX功能_DDF Model 新增，Port-X > Item-X 新增 ProtocolType HLLT | ARCHIE.YANG 楊浩群 | Completed
2 hours | 1 hour 30 mins | Rev1.14.0 DIADesigner | Task | 581412 | [RD_DEV] W3A 下載管理員內資料交換表與參數編輯器項目新增同步邏輯 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 42 mins | Rev1.14.0 DIADesigner | Task | 581118 | [RD_DEV] W3A 上下載管理員使用模擬器時禁止勾選參數編輯器項目 | ARCHIE.YANG 楊浩群 | Completed
8 hours | 6 hours | Designer Rev1.14.0 Sprint3 | Task | 581076 | [RD_DEV][W3A] 擴充 0x48 錯誤訊息多國語系 | JENNY.HY.CHEN 陳湘筠 | Completed
12 hours | 8 hours | Designer Rev1.14.0 Sprint3 | Task | 581075 | [RD_DEV][W3A] 擴充 0x48 sfc3 封包格式 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 8 hours 30 mins | Rev1.14.0 DIADesigner | Task | 580791 | [RD_DEV] (硬體配置) AS300EC 機種從硬體配置新增功能卡會出現Exception | NANCY.TC.YANG 楊采真 | Completed
4 hours | 4 hours | Rev1.14.0 DIADesigner | Task | 580709 | [RD_DEV] Migrate DdfCheck from DIAOneWeb.WebAPI to DIADesigner | MILENA.CHEN 陳孟歆 | Completed
8 hours | 6 hours | Rev1.14.0 DIADesigner | Task | 580436 | [RD_DEV] (硬體配置) 取消轉送設定後開啟網路視圖參數設定被竄改 | NANCY.TC.YANG 楊采真 | Completed
2 hours | 1 hour 30 mins | Designer Rev1.14.0 Sprint2 | Task | 580409 | [RD_DEV] VFD CSV, XLSX 參數匯出不把空白的 Unit 輸出成 '#' | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour | Rev1.14.0 DIADesigner | Task | 579941 | [RD_DEV] 修正 DVP Scan 未還原整合 DIO 模組的問題 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 579812 | [RD_DEV] DVP 改用 ProdSubseries 判斷還原整合 DIO 模組 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 579798 | [RD_DEV] 修正 ASD 在上載管理員消失的問題 | ARCHIE.YANG 楊浩群 | Completed
30 mins | 30 mins | Rev1.14.0 DIADesigner | Task | 579586 | [RD_DEV] W3A 連線時的驗證結果需保存 | ARCHIE.YANG 楊浩群 | Completed
24 hours | 10 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 579571 | [RD_DEV] W3A上載新增設備時, 須初始化 Embedded Device 通訊 | XAVIERA.FAN 范珮欣 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 579545 | [RD_DEV][W3A] 示波器簡化PLC位置不合法錯誤資訊 | JENNY.HY.CHEN 陳湘筠 | Completed
1 hour | 27 mins | Designer Rev1.14.0 Sprint2 | Task | 579528 | [RD_DEV] 修正上載管理員內加入新裝置時沒有顯示節點 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 579337 | [RD_DEV] 新增 A3-EP 的 Device ID Code | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour 30 mins | Rev1.14.0 DIADesigner | Task | 579293 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Asd.*) | ARCHIE.YANG 楊浩群 | Completed
3 hours | 2 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 579204 | [RD_DEV] VFD: online 時, 狀態列顯示錯誤 | XAVIERA.FAN 范珮欣 | Completed
30 mins | 48 mins | Rev1.14.0 DIADesigner | Task | 579026 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Corner.Communication) | ARCHIE.YANG 楊浩群 | Completed
2 hours | 2 hours | Rev1.14.0 DIADesigner | Task | 578957 | [RD_DEV] 修正寫 Device.xml Document NodeType 行為 | MILENA.CHEN 陳孟歆 | Completed
4 hours | 3 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 578818 | [RD_DEV][JIRA] (專案管理) [IABGVOC-1786] DIADesigner专案名字有写小数点的版本号时，如果另外档案，目前会把最后一个小数点的数值删除掉 | NANCY.TC.YANG 楊采真 | Completed
8 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 578750 | [RD_DEV]支援ASD A3-EX功能 POC_DDF | MILENA.CHEN 陳孟歆 | In Progress
1 hour | 1 hour | Rev1.14.0 DIADesigner | Task | 578719 | [RD_DEV] 修正 TC 無法下載的問題 (Check 失敗) | ARCHIE.YANG 楊浩群 | Completed
3 hours | 5 hours | Rev1.14.0 DIADesigner | Task | 578693 | [RD_DEV] 改善上下載管理員效能 (ASD、VFD 有大量參數節點時) | ARCHIE.YANG 楊浩群 | Completed
4 hours | 5 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 578350 | [RD_DEV]支援ASD A3-EX功能 POC_Online/Offline_SRS | NANCY.TC.YANG 楊采真 | Completed
2 hours | 3 hours | Designer Rev1.14.0 Sprint2 | Task | 578176 | [RD_DEV][W3A] 使用 W3A 模擬器連線示波器的情況下，監控項目若有 Servo Normal 則要跳警告視窗 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 578175 | [RD_DEV][W3A] 示波器監測項目為零的警告視窗增加易讀描述 | JENNY.HY.CHEN 陳湘筠 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 578174 | [RD_DEV][W3A] 進入多頻道模式時，應禁用各自座標系 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 578171 | [RD_DEV][W3A] 多通道示波器監控時，多通道 Y 軸沒有自動調整範圍 | JENNY.HY.CHEN 陳湘筠 | Completed
12 hours | 11 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 578140 | [RD_DEV]支援ASD A3-EX功能 POC_DI DO function configuration Requirement_SRS | NANCY.TC.YANG 楊采真 | Resolved
1 hour | 1 hour 42 mins | Rev1.14.0 DIADesigner | Task | 578123 | [RD_DEV](線上模式) 線上模式匹配不符時， 英文的提示字會被切掉 | NANCY.TC.YANG 楊采真 | Completed
4 hours | 2 hours 9 mins | Rev1.14.0 DIADesigner | Task | 578070 | [RD_DEV](新增裝置) When clicking a node in the project tree with the mouse, the focused item does not display a colored background. (3/3) | NANCY.TC.YANG 楊采真 | Completed
8 hours | 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577958 | [RD_DEV]支援ASD A3-EX功能 POC_Ethernet Connection Requirement_SRS | NANCY.TC.YANG 楊采真 | Completed
4 hours | 4 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 577777 | [RD_DEV](網路配置) 项目树与网络视图控制，联动，可同时选中 | NANCY.TC.YANG 楊采真 | Completed
30 mins | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577624 | [RD_DEV] DVP16SV3_機種轉換 | NANCY.TC.YANG 楊采真 | Completed
4 hours | 4 hours | Designer Rev1.14.0 Sprint3 | Task | 577623 | [RD_DEV] DVP16SV3_示波器 | JOHNNY.MC.YEH 葉明勳 | Completed
8 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577620 | [RD_DEV] DVP16SV3_裝置與錯誤資訊 | MILENA.CHEN 陳孟歆 | Completed
2 hours | 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 577619 | [RD_DEV] DVP16SV3_參數編輯器 | NANCY.TC.YANG 楊采真 | Completed
2 hours | 2 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 577484 | [RD_DEV] APF3000_網路視圖 (離線功能) | CLONE.LIN 林俊淵 | Completed
1 hour | 30 mins | Rev1.14.0 DIADesigner | Task | 577354 | [RD_DEV] 修正 SetupDiGetClassDevs 回傳值的判斷方式 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 42 mins | Rev1.14.0 DIADesigner | Task | 577139 | [RD_DEV] 支援無配置時以預設行為初始化 CommgrHelper | ARCHIE.YANG 楊浩群 | Completed
1 hour | 42 mins | Rev1.14.0 DIADesigner | Task | 577137 | [RD_DEV] 修正判斷 ASDASoft Process 的邏輯，避免問錯對象，反覆發生例外 | ARCHIE.YANG 楊浩群 | Completed
6 hours | 8 hours | Rev1.14.0 DIADesigner | Task | 577088 | [RD_DEV] W3A 增加 Servo 參數編輯器與上下載項目 | ARCHIE.YANG 楊浩群 | Completed
16 hours | 16 hours | Designer Rev1.14.0 Sprint2 | Task | 577069 | [RD_DEV] (網路配置)网络视图，拖拽链接时，不应该自动修改通讯地址，建议增加跳转可编辑选项 | CLONE.LIN 林俊淵 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Sprint2 | Task | 577005 | [RD_DEV]W3A EtherCAT 拓樸圖從站 Advance Option 禁用 revision 檢查 | WILLIAM.HC.SHEN 沈桓慶 | Completed
16 hours | 14 hours | Designer Rev1.14.0 Sprint2 | Task | 577004 | [RD_DEV]ECAT PDO配置UI優化 (新增PDO, 清單畫面不要跳至第一項/ 新增PDO參數做標示) | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 10 hours | Designer Rev1.14.0 Sprint2 | Task | 576998 | [RD_DEV]ECAT從站客製化名稱要同步到軸上 | WILLIAM.HC.SHEN 沈桓慶 | Completed
16 hours | 28 hours | Designer Rev1.14.0 Sprint2 | Task | 576996 | [RD_DEV] EtherCAT ToolBar 添加 datagram 使用量 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Sprint2 | Task | 576994 | [RD_DEV]修改 ECAT 站號排列規則，從1001起 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 8 hours 12 mins | Designer Rev1.14.0 Sprint2 | Task | 576903 | [RD_DEV](專案管理) 當任一裝置切換成線上模式時，DIADesigner 應一律禁止上載下載行為 | NANCY.TC.YANG 楊采真 | Completed
2 hours | 2 hours | Designer Rev1.14.0 Sprint1 | Task | 576755 | [RD_DEV] 示波器停用動畫功能以提升效能，減少不必要運算 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 576748 | [RD_DEV] PLC logger & Tracer 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 10 hours | Designer Rev1.14.0 Sprint2 | Task | 576747 | [RD_DEV][W3A] W3A 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 576746 | [RD_DEV] VFD 示波器加入 undo/redo 功能 | JENNY.HY.CHEN 陳湘筠 | Completed
2 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 576740 | [RD_DEV][W3A] 多畫布加入 visibleRange 變更事件 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Sprint3 | Task | 576491 | [RD_DEV][W3A] EtherCAT IO 映射表提供 sub channel 資訊給編譯器 | WILLIAM.HC.SHEN 沈桓慶 | Completed
12 hours | 12 hours | Designer Rev1.14.0 Sprint2 | Task | 576481 | [RD_DEV]新增台達裝置從裝置樹批次添加功能 | WILLIAM.HC.SHEN 沈桓慶 | Completed
12 hours | 12 hours | Designer Rev1.14.0 Sprint2 | Task | 576480 | [RD_DEV]新增總線裝置批次添加功能 | WILLIAM.HC.SHEN 沈桓慶 | Completed
4 hours | 4 hours | Rev1.14.0 DIADesigner | Task | 576409 | [RD_DEV]匯入不支援的Modbustcp版本或是不相同的Field Bus要防呆 | FRANKNC.HO 何南瑾 | Completed
2 hours | 2 hours | Rev1.14.0 DIADesigner | Task | 576366 | [RD_DEV] 刪除 ASD 裝置時應正確釋放參數編輯器 | ARCHIE.YANG 楊浩群 | Completed
32 hours | 17 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 576235 | [RD_DEV]DURApulse Designer 2st Beta SW Review Reply_20260413 | NANCY.TC.YANG 楊采真 | Completed
24 hours | 18 hours | Designer Rev1.14.0 Sprint3 | Task | 576071 | [RD_DEV] 規劃如何讓Security Main Process運行在既有Designer版本流程上 | NANCY.TC.YANG 楊采真 | In Progress
1 hour | 1 hour 30 mins | Rev1.14.0 DIADesigner | Task | 576006 | [RD_DEV] 調整 MODBUS 接收資料的預設 Delay 為 0 | ARCHIE.YANG 楊浩群 | Completed
1 hour | 1 hour 30 mins | Designer Rev1.14.0 Sprint3 | Task | 575993 | (Cyber Security) Regular review process of Main Process | CLONE.LIN 林俊淵 | Completed
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 575864 | (Cyber Security) Regular review process of General Review Process | CLONE.LIN 林俊淵 | Completed
8 hours | 2 hours | Designer Rev1.14.0 Plan | Task | 575846 | [RD_DEV][W3A] 示波器增加最小、最大、平均值顯示欄位 | JENNY.HY.CHEN 陳湘筠 | Completed
24 hours | 10 hours | Designer Rev1.14.0 Sprint3 | Task | 575705 | (Cyber Security) Regular review process of TMRA Process | JANET.JC.CHEN 陳美蓁 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 575221 | [RD_DEV] DVPSEC - 通訊: 上載 App Compact Bin, 固化方案版號, Program Checksum | XAVIERA.FAN 范珮欣 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint2 | Task | 575219 | [RD_DEV] DVPSEC - 通訊: 下載 Program Checksum 與 固化方案版號 | XAVIERA.FAN 范珮欣 | Completed
8 hours | 3 hours | Designer Rev1.14.0 Sprint3 | Task | 575110 | [RD_DEV] CANopen 掃描通訊: 提供 Unknown Device 的識別資訊 | XAVIERA.FAN 范珮欣 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 574840 | [RD_DEV] MA500_通訊測試工具 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 574839 | [RD_DEV] MA500_示波器 | JENNY.HY.CHEN 陳湘筠 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 574838 | [RD_DEV] MA500_數位操作器 | JENNY.HY.CHEN 陳湘筠 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 574836 | [RD_DEV] MA500_裝置與錯誤資訊 | MILENA.CHEN 陳孟歆 | Completed
8 hours | 2 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574834 | [RD_DEV] MA500_參數編輯器 | NANCY.TC.YANG 楊采真 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574832 | [RD_DEV] MA500_通訊設定 | XAVIERA.FAN 范珮欣 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574831 | [RD_DEV] MA500_變頻精靈 | XAVIERA.FAN 范珮欣 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 574830 | [RD_DEV] MA500_新增裝置 | MILENA.CHEN 陳孟歆 | Completed
8 hours | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 574829 | [RD_DEV] MA500_DDF (新機種) | MILENA.CHEN 陳孟歆 | Completed
4 hours | 1 hour | Designer Rev1.14.0 Sprint2 | Task | 574813 | [RD_DEV] APF3000_新增裝置 & DDF/EDS (release 前移除) | MILENA.CHEN 陳孟歆 | Completed
2 hours | 1 hour | Designer Rev1.14.0 Sprint1 | Task | 574786 | [RD_DEV] MX300-S_新增裝置 & DDF (新機種) | MILENA.CHEN 陳孟歆 | Completed
8 hours | 4 hours | Designer Rev1.14.0 Plan | Task | 574667 | [RD_DEV] EtherCAT_Tag_Table 變數名稱異常 | WILLIAM.HC.SHEN 沈桓慶 | Completed
8 hours | 1 hour 36 mins | Designer Rev1.14.0 Sprint2 | Task | 574659 | [RD_DEV] AS332EC - 通訊: 取得 Program Checksum 與 固化方案版號 | XAVIERA.FAN 范珮欣 | Completed
12 hours | 6 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 574652 | [RD_DEV] AS332EC - 通訊: 下載 固化方案版號 與 Program Checksum | XAVIERA.FAN 范珮欣 | Completed
24 hours | 5 hours 6 mins | Designer Rev1.14.0 Sprint2 | Task | 574651 | [RD_DEV] AS332EC - 通訊: 上載 App Compact Bin | XAVIERA.FAN 范珮欣 | Completed
1 hour | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 574005 | [RD_DEV] 通訊設定: 驗證 W3A 預設站號為 200 | XAVIERA.FAN 范珮欣 | Completed
24 hours | 8 hours | Designer Rev1.14.0 Sprint3 | Task | 574003 | [RD_DEV] 通訊設定: 預設站號從 DDF 取得 | XAVIERA.FAN 范珮欣 | Completed
8 hours | 9 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 573572 | [RD_DEV] HMI 圖檔 | MILENA.CHEN 陳孟歆 | Completed
16 hours | 9 hours 30 mins | Designer Rev1.14.0 Sprint2 | Task | 573571 | [RD_DEV] HMI NW | CLONE.LIN 林俊淵 | Completed
16 hours | 2 hours | Designer Rev1.14.0 Sprint1 | Task | 572752 | [RD_DEV] 初步驗證 B5 下載 | JEAN.LC.WANG 王儷臻 | In Progress
40 hours | 20 hours | Rev1.14.0 DIADesigner | Task | 572194 | [RD_DEV] 1.14.0 PJM & PMO Related work | NANCY.TC.YANG 楊采真 | In Progress
16 hours | 6 hours | Designer Rev1.14.0 Plan | Task | 570316 | [RD_DEV][W3A] 示波器停止時最小、最大、平均值隨畫面範圍內的數值變化 | JENNY.HY.CHEN 陳湘筠 | Completed
3 hours | 3 hours | Designer Rev1.14.0 Sprint3 | Task | 569952 | [RD_DEV] DVP16SV3 HW存讀檔需容舊型號 | ARCHIE.YANG 楊浩群 | Completed
24 hours | 12 hours | Designer Rev1.14.0 Plan | Task | 564806 | [RD_DEV]當使用者配置的 EtherCAT 從站項目，有超出 FECAT 或 DVP-ES3(TEC) 限制的 pdo entry數量時，跳出警告 | WILLIAM.HC.SHEN 沈桓慶 | In Progress
40 hours | 5 hours | Rev1.14.0 DIADesigner | Task | 560172 | [RD_DEV] 修改SAS內容 | NANCY.TC.YANG 楊采真 | Completed
16 hours | 12 hours | Rev1.14.0 DIADesigner | Task | 558807 | [RD_DEV] 申請表併入SAS、參數對應表、SRS等文件 | NANCY.TC.YANG 楊采真 | Completed
16 hours | 10 hours | Designer Rev1.14.0 Plan | Task | 540114 | [RD_DEV][W3A] 示波器導入VFD示波器的事件觸發功能 | JENNY.HY.CHEN 陳湘筠 | In Progress
8 hours | 15 mins | Rev1.14.0 DIADesigner | Task | 532083 | [RD_DEV] VFD_資料交換表文件範圍確認與更新 | NANCY.TC.YANG 楊采真 | Resolved
40 hours | 19 hours | Rev1.14.0 DIADesigner | Task | 527017 | [RD_DEV][W3A]通訊參數設定-下載通訊相關參數 | ARCHIE.YANG 楊浩群 | Completed
40 hours | 12 hours 6 mins | Rev1.14.0 DIADesigner | Task | 527016 | [RD_DEV][W3A]通訊參數設定-上載通訊相關參數 | ARCHIE.YANG 楊浩群 | Completed
4 hours | 4 hours | Designer Rev1.14.0 Sprint2 | Task | 526437 | [RD_DEV][W3A] Corner 示波器各CH獨立頻寬操作 - 配合機種DDF來呈現取樣頻率清單 | JENNY.HY.CHEN 陳湘筠 | Completed
8 hours | 2 hours | Designer Rev1.14.0 Sprint2 | Task | 525431 | [RD_DEV][W3A] - 產品包驗證 | JEAN.LC.WANG 王儷臻 | In Progress
1 hour | 1 hour | Designer Rev1.14.0 Sprint3 | Task | 525119 | [RD_DEV] AS332EC - 設備主體: 無法執行 PLC EIP Scan 功能 | CLONE.LIN 林俊淵 | Completed
4 hours | 2 hours 18 mins | Rev1.14.0 DIADesigner | Task | 523127 | [RD_DEV] VFD_裝置Online/Offline資訊文件範圍確認(Config) | NANCY.TC.YANG 楊采真 | Completed
40 hours | 1 hour | Rev1.14.0 DIADesigner | Task | 523123 | [RD_DEV] VFD_調適資訊文件範圍確認與更新_Config | NANCY.TC.YANG 楊采真 | Resolved
2 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 522702 | [RD_DEV] DVPSEC - Check NW PC Scan 是否可找到 DVPSEC | CLONE.LIN 林俊淵 | Completed
4 hours | 30 mins | Designer Rev1.14.0 Sprint3 | Task | 522701 | [RD_DEV] DVPSEC - Check NW 是否可執行PLC EIP Scan功能 | CLONE.LIN 林俊淵 | Completed
8 hours | 6 hours 30 mins | Designer Rev1.14.0 Sprint3 | Task | 521989 | [RD_DEV] DVPSEC - Embedded Corner下載管理員: Post Download | XAVIERA.FAN 范珮欣 | Resolved
0 hours | 0 hours | Designer Rev1.14.0 Plan | Task | 518202 | [RD_DEV] IO-Link Device 監控頁面 | CLONE.LIN 林俊淵 | Completed
16 hours | 16 hours 30 mins | Designer Rev1.14.0 Plan | Task | 518201 | [RD_DEV] IO-Link Master 監控頁面 | CLONE.LIN 林俊淵 | Completed
0 hours | 0 hours | Designer Rev1.14.0 Plan | Task | 518198 | [RD_DEV] IO-Link Device 設定頁面 - Process Data 分頁 | FRANKNC.HO 何南瑾 | Completed
56 hours | 1 hour 18 mins | Designer Rev1.14.0 Plan | Task | 518197 | [RD_DEV] IO-Link Device 設定頁面 - Parameter 分頁 | KAKA.WU 吳思言 | Completed
32 hours | 24 hours | Designer Rev1.14.0 Plan | Task | 518196 | [RD_DEV] IO-Link Master 設定頁面 - Process Data 分頁 | CLONE.LIN 林俊淵 | Completed
16 hours | 4 hours 30 mins | Designer Rev1.14.0 Sprint1 | Task | 507752 | [RD_DEV] DIADesigner shall be able to download/upload via the AS-FFTP01 card | CLONE.LIN 林俊淵 | Completed
4 hours | 2 hours | Designer Rev1.14.0 Sprint3 | Task | 507452 | [RD_DEV] AS332EC - 通訊: 連線至模擬器 | XAVIERA.FAN 范珮欣 | Assigned
4 hours | 3 hours | Designer Rev1.14.0 Sprint2 | Task | 505435 | [RD_DEV] VA3000_新增裝置 & DDF (release 前移除) | MILENA.CHEN 陳孟歆 | Completed
16 hours | 14 hours | Designer Rev1.14.0 Sprint2 | Task | 499614 | [RD_DEV] AS332EC - Corner 產品包驗證 | JEAN.LC.WANG 王儷臻 | In Progress
24 hours | 2 hours | Rev1.14.0 DIADesigner | Task | 484525 | [RD_DEV] ADC客製案_Architecture Design_採用注入方式 | ARCHIE.YANG 楊浩群 | In Progress