## Summary
ESTIMATE DASHBOARD ¦ Owner Summary
Total Estimate | Total TimeSpend | Utilization Rate | Total Tasks
1099.5h | 587.8h | 53.5% | 130

## _ChartData (hidden)
Owner | Estimate(h) | TimeSpend(h) | Sprint | Estimate(h) | TimeSpend(h)
ARCHIE | 146 | 75.1 | Plan | 176 | 75.8
CLONE | 108 | 80 | Sprint1 | 36 | 9.5
FRANKNC | 4 | 4 | Sprint2 | 289 | 217.6
JANET | 24 | 10 | Sprint3 | 291.5 | 155.2
JEAN | 40 | 18 | DIADesigner | 307 | 129.7
JENNY | 110 | 68
JOHNNY | 4 | 4
KAKA | 56 | 1.3
MILENA | 56 | 25.5
NANCY | 275.5 | 133.1
WILLIAM | 144 | 120.5
XAVIERA | 132 | 48.3
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint2 | 4 | 3
[6 empty] | Sprint3 | 14 | 11.2
[6 empty] | DIADesigner | 128 | 60.9
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 48 | 40.5
[6 empty] | Sprint1 | 16 | 4.5
[6 empty] | Sprint2 | 34 | 28
[6 empty] | Sprint3 | 10 | 7
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | DIADesigner | 4 | 4
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint3 | 24 | 10
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint1 | 16 | 2
[6 empty] | Sprint2 | 24 | 16
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 40 | 18
[6 empty] | Sprint1 | 2 | 2
[6 empty] | Sprint2 | 40 | 31
[6 empty] | Sprint3 | 28 | 17
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint3 | 4 | 4
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 56 | 1.3
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint1 | 2 | 1
[6 empty] | Sprint2 | 16 | 13.5
[6 empty] | Sprint3 | 32 | 5
[6 empty] | DIADesigner | 6 | 6
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint2 | 16 | 15.8
[6 empty] | Sprint3 | 90.5 | 58.5
[6 empty] | DIADesigner | 169 | 58.8
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 32 | 16
[6 empty] | Sprint2 | 80 | 84
[6 empty] | Sprint3 | 32 | 20.5
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint2 | 75 | 26.3
[6 empty] | Sprint3 | 57 | 22

## ARCHIE
ARCHIE.YANG 楊浩群
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 146.0h | 75.1h | 51.4% | 31
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583575 | [RD_DEV] 新增 DIO 調機 Icon | Designer Rev1.14.0 Sprint3 | Task | Completed | 0.5 | 0.1 | -0.4
583543 | [RD_DEV] 開啟通訊設定視窗時更新專案樹呈現的裝置連線狀況 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.4 | -0.6
583532 | [RD_DEV] 新增不做資料處理的 ModbusProtocolBase，新增可自訂 IConnector 的 Ethernet 設定物件 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 3.3 | -0.7
583509 | [RD_DEV] ETH 通訊設定改用統一的 Element Name 儲存 | Designer Rev1.14.0 Sprint3 | Task | Completed | 2 | 1.9 | -0.1
583499 | [RD_DEV] 調整 ASD Run/Stop 狀態訊息為 Servo On/Off | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.8 | -0.2
582453 | [RD_DEV] 修正建立上下載項目的最上層過濾條件 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.6 | 0.6
582291 | [RD_DEV] VFD Monitor Table 釋放時需先關閉頁籤再釋放底層物件 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.8 | -0.2
582128 | [RD_DEV] 支援ASD A3-EX功能_DDF Model 新增，Port-X > Item-X 新增 ProtocolType HLLT | Designer Rev1.14.0 Sprint3 | Task | Completed | 0.5 | 0.2 | -0.3
581412 | [RD_DEV] W3A 下載管理員內資料交換表與參數編輯器項目新增同步邏輯 | Rev1.14.0 DIADesigner | Task | Completed | 2 | 1.5 | -0.5
581118 | [RD_DEV] W3A 上下載管理員使用模擬器時禁止勾選參數編輯器項目 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.7 | -0.3
580409 | [RD_DEV] VFD CSV, XLSX 參數匯出不把空白的 Unit 輸出成 '#' | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 1.5 | -0.5
579941 | [RD_DEV] 修正 DVP Scan 未還原整合 DIO 模組的問題 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1 | 0
579812 | [RD_DEV] DVP 改用 ProdSubseries 判斷還原整合 DIO 模組 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
579798 | [RD_DEV] 修正 ASD 在上載管理員消失的問題 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 1 | 0
579586 | [RD_DEV] W3A 連線時的驗證結果需保存 | Rev1.14.0 DIADesigner | Task | Completed | 0.5 | 0.5 | 0
579528 | [RD_DEV] 修正上載管理員內加入新裝置時沒有顯示節點 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 0.5 | -0.5
579337 | [RD_DEV] 新增 A3-EP 的 Device ID Code | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.5 | -0.5
579293 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Asd.*) | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.5 | 0.5
579026 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Corner.Communication) | Rev1.14.0 DIADesigner | Task | Completed | 0.5 | 0.8 | 0.3
578719 | [RD_DEV] 修正 TC 無法下載的問題 (Check 失敗) | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1 | 0
578693 | [RD_DEV] 改善上下載管理員效能 (ASD、VFD 有大量參數節點時) | Rev1.14.0 DIADesigner | Task | Completed | 3 | 5 | 2
577354 | [RD_DEV] 修正 SetupDiGetClassDevs 回傳值的判斷方式 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.5 | -0.5
577139 | [RD_DEV] 支援無配置時以預設行為初始化 CommgrHelper | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.7 | -0.3
577137 | [RD_DEV] 修正判斷 ASDASoft Process 的邏輯，避免問錯對象，反覆發生例外 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.7 | -0.3
577088 | [RD_DEV] W3A 增加 Servo 參數編輯器與上下載項目 | Rev1.14.0 DIADesigner | Task | Completed | 6 | 8 | 2
576366 | [RD_DEV] 刪除 ASD 裝置時應正確釋放參數編輯器 | Rev1.14.0 DIADesigner | Task | Completed | 2 | 2 | 0
576006 | [RD_DEV] 調整 MODBUS 接收資料的預設 Delay 為 0 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.5 | 0.5
569952 | [RD_DEV] DVP16SV3 HW存讀檔需容舊型號 | Designer Rev1.14.0 Sprint3 | Task | Completed | 3 | 3 | 0
527017 | [RD_DEV][W3A]通訊參數設定-下載通訊相關參數 | Rev1.14.0 DIADesigner | Task | Completed | 40 | 19 | -21
527016 | [RD_DEV][W3A]通訊參數設定-上載通訊相關參數 | Rev1.14.0 DIADesigner | Task | Completed | 40 | 12.1 | -27.9
484525 | [RD_DEV] ADC客製案_Architecture Design_採用注入方式 | Rev1.14.0 DIADesigner | Task | In Progress | 24 | 2 | -22

## CLONE
CLONE.LIN 林俊淵
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 108.0h | 80.0h | 74.1% | 13
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583940 | [RD_DEV] 網路視圖在特定操作下刪除總線網路會發生線段殘留現象 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
577484 | [RD_DEV] APF3000_網路視圖 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 2.5 | 0.5
577069 | [RD_DEV] (網路配置)网络视图，拖拽链接时，不应该自动修改通讯地址，建议增加跳转可编辑选项 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 16 | 0
575993 | (Cyber Security) Regular review process of Main Process | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1.5 | 0.5
575864 | (Cyber Security) Regular review process of General Review Process | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
573571 | [RD_DEV] HMI NW | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 9.5 | -6.5
525119 | [RD_DEV] AS332EC - 設備主體: 無法執行 PLC EIP Scan 功能 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
522702 | [RD_DEV] DVPSEC - Check NW PC Scan 是否可找到 DVPSEC | Designer Rev1.14.0 Sprint3 | Task | Completed | 2 | 2 | 0
522701 | [RD_DEV] DVPSEC - Check NW 是否可執行PLC EIP Scan功能 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0.5 | -3.5
518202 | [RD_DEV] IO-Link Device 監控頁面 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 0 | 0
518201 | [RD_DEV] IO-Link Master 監控頁面 | Designer Rev1.14.0 Plan | Task | Completed | 16 | 16.5 | 0.5
518196 | [RD_DEV] IO-Link Master 設定頁面 - Process Data 分頁 | Designer Rev1.14.0 Plan | Task | Completed | 32 | 24 | -8
507752 | [RD_DEV] DIADesigner shall be able to download/upload via the AS-FFTP01 card | Designer Rev1.14.0 Sprint1 | Task | Completed | 16 | 4.5 | -11.5

## FRANKNC
FRANKNC.HO 何南瑾
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 4.0h | 4.0h | 100.0% | 2
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
576409 | [RD_DEV]匯入不支援的Modbustcp版本或是不相同的Field Bus要防呆 | Rev1.14.0 DIADesigner | Task | Completed | 4 | 4 | 0
518198 | [RD_DEV] IO-Link Device 設定頁面 - Process Data 分頁 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 0 | 0

## JANET
JANET.JC.CHEN 陳美蓁
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 24.0h | 10.0h | 41.7% | 1
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
575705 | (Cyber Security) Regular review process of TMRA Process | Designer Rev1.14.0 Sprint3 | Task | Completed | 24 | 10 | -14

## JEAN
JEAN.LC.WANG 王儷臻
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 40.0h | 18.0h | 45.0% | 3
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
572752 | [RD_DEV] 初步驗證 B5 下載 | Designer Rev1.14.0 Sprint1 | Task | In Progress | 16 | 2 | -14
525431 | [RD_DEV][W3A] - 產品包驗證 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 8 | 2 | -6
499614 | [RD_DEV] AS332EC - Corner 產品包驗證 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 16 | 14 | -2

## JENNY
JENNY.HY.CHEN 陳湘筠
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 110.0h | 68.0h | 61.8% | 20
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
582732 | [RD_DEV] MX300 keypad 取值失敗時不應清空數值及單位 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 3 | -1
581076 | [RD_DEV][W3A] 擴充 0x48 錯誤訊息多國語系 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 6 | -2
581075 | [RD_DEV][W3A] 擴充 0x48 sfc3 封包格式 | Designer Rev1.14.0 Sprint3 | Task | Completed | 12 | 8 | -4
579545 | [RD_DEV][W3A] 示波器簡化PLC位置不合法錯誤資訊 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 1 | 0
578176 | [RD_DEV][W3A] 使用 W3A 模擬器連線示波器的情況下，監控項目若有 Servo Normal 則要跳警告視窗 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 3 | 1
578175 | [RD_DEV][W3A] 示波器監測項目為零的警告視窗增加易讀描述 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 1 | -1
578174 | [RD_DEV][W3A] 進入多頻道模式時，應禁用各自座標系 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 1 | 0
578171 | [RD_DEV][W3A] 多通道示波器監控時，多通道 Y 軸沒有自動調整範圍 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 2 | 0
576755 | [RD_DEV] 示波器停用動畫功能以提升效能，減少不必要運算 | Designer Rev1.14.0 Sprint1 | Task | Completed | 2 | 2 | 0
576748 | [RD_DEV] PLC logger & Tracer 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 2 | 0
576747 | [RD_DEV][W3A] W3A 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 10 | 2
576746 | [RD_DEV] VFD 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 2 | -2
576740 | [RD_DEV][W3A] 多畫布加入 visibleRange 變更事件 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 1 | -1
575846 | [RD_DEV][W3A] 示波器增加最小、最大、平均值顯示欄位 | Designer Rev1.14.0 Plan | Task | Completed | 8 | 2 | -6
574840 | [RD_DEV] MA500_通訊測試工具 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 1 | -3
574839 | [RD_DEV] MA500_示波器 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 1 | -7
574838 | [RD_DEV] MA500_數位操作器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 2 | -2
570316 | [RD_DEV][W3A] 示波器停止時最小、最大、平均值隨畫面範圍內的數值變化 | Designer Rev1.14.0 Plan | Task | Completed | 16 | 6 | -10
540114 | [RD_DEV][W3A] 示波器導入VFD示波器的事件觸發功能 | Designer Rev1.14.0 Plan | Task | In Progress | 16 | 10 | -6
526437 | [RD_DEV][W3A] Corner 示波器各CH獨立頻寬操作 - 配合機種DDF來呈現取樣頻率清單 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 4 | 0

## JOHNNY
JOHNNY.MC.YEH 葉明勳
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 4.0h | 4.0h | 100.0% | 1
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
577623 | [RD_DEV] DVP16SV3_示波器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 4 | 0

## KAKA
KAKA.WU 吳思言
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 56.0h | 1.3h | 2.3% | 1
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
518197 | [RD_DEV] IO-Link Device 設定頁面 - Parameter 分頁 | Designer Rev1.14.0 Plan | Task | Completed | 56 | 1.3 | -54.7

## MILENA
MILENA.CHEN 陳孟歆
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 56.0h | 25.5h | 45.5% | 11
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
580709 | [RD_DEV] Migrate DdfCheck from DIAOneWeb.WebAPI to DIADesigner | Rev1.14.0 DIADesigner | Task | Completed | 4 | 4 | 0
578957 | [RD_DEV] 修正寫 Device.xml Document NodeType 行為 | Rev1.14.0 DIADesigner | Task | Completed | 2 | 2 | 0
578750 | [RD_DEV]支援ASD A3-EX功能 POC_DDF | Designer Rev1.14.0 Sprint3 | Task | In Progress | 8 | 0.5 | -7.5
577620 | [RD_DEV] DVP16SV3_裝置與錯誤資訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 0.5 | -7.5
574836 | [RD_DEV] MA500_裝置與錯誤資訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 2 | -2
574830 | [RD_DEV] MA500_新增裝置 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 1 | -3
574829 | [RD_DEV] MA500_DDF (新機種) | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 1 | -7
574813 | [RD_DEV] APF3000_新增裝置 & DDF/EDS (release 前移除) | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 1 | -3
574786 | [RD_DEV] MX300-S_新增裝置 & DDF (新機種) | Designer Rev1.14.0 Sprint1 | Task | Completed | 2 | 1 | -1
573572 | [RD_DEV] HMI 圖檔 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 9.5 | 1.5
505435 | [RD_DEV] VA3000_新增裝置 & DDF (release 前移除) | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 3 | -1

## NANCY
NANCY.TC.YANG 楊采真
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 275.5h | 133.1h | 48.3% | 21
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
580791 | [RD_DEV] (硬體配置) AS300EC 機種從硬體配置新增功能卡會出現Exception | Rev1.14.0 DIADesigner | Task | Completed | 8 | 8.5 | 0.5
580436 | [RD_DEV] (硬體配置) 取消轉送設定後開啟網路視圖參數設定被竄改 | Rev1.14.0 DIADesigner | Task | Completed | 8 | 6 | -2
578818 | [RD_DEV][JIRA] (專案管理) [IABGVOC-1786] DIADesigner专案名字有写小数点的版本号时，如果另外档案，目前会把最后一个小数点的数值删除掉 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 3.5 | -0.5
578350 | [RD_DEV]支援ASD A3-EX功能 POC_Online/Offline_SRS | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 5.5 | 1.5
578140 | [RD_DEV]支援ASD A3-EX功能 POC_DI DO function configuration Requirement_SRS | Designer Rev1.14.0 Sprint3 | Task | Resolved | 12 | 11.5 | -0.5
578123 | [RD_DEV](線上模式) 線上模式匹配不符時， 英文的提示字會被切掉 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.7 | 0.7
578070 | [RD_DEV](新增裝置) When clicking a node in the project tree with the mouse, the focused item does not display a colored background. (3/3) | Rev1.14.0 DIADesigner | Task | Completed | 4 | 2.1 | -1.9
577958 | [RD_DEV]支援ASD A3-EX功能 POC_Ethernet Connection Requirement_SRS | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 1.5 | -6.5
577777 | [RD_DEV](網路配置) 项目树与网络视图控制，联动，可同时选中 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 4.1 | 0.1
577624 | [RD_DEV] DVP16SV3_機種轉換 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0.5 | 0.5 | 0
577619 | [RD_DEV] DVP16SV3_參數編輯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 2 | 1.5 | -0.5
576903 | [RD_DEV](專案管理) 當任一裝置切換成線上模式時，DIADesigner 應一律禁止上載下載行為 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 8.2 | 0.2
576235 | [RD_DEV]DURApulse Designer 2st Beta SW Review Reply_20260413 | Designer Rev1.14.0 Sprint3 | Task | Completed | 32 | 17.5 | -14.5
576071 | [RD_DEV] 規劃如何讓Security Main Process運行在既有Designer版本流程上 | Designer Rev1.14.0 Sprint3 | Task | In Progress | 24 | 18 | -6
574834 | [RD_DEV] MA500_參數編輯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 2.5 | -5.5
572194 | [RD_DEV] 1.14.0 PJM & PMO Related work | Rev1.14.0 DIADesigner | Task | In Progress | 40 | 20 | -20
560172 | [RD_DEV] 修改SAS內容 | Rev1.14.0 DIADesigner | Task | Completed | 40 | 5 | -35
558807 | [RD_DEV] 申請表併入SAS、參數對應表、SRS等文件 | Rev1.14.0 DIADesigner | Task | Completed | 16 | 12 | -4
532083 | [RD_DEV] VFD_資料交換表文件範圍確認與更新 | Rev1.14.0 DIADesigner | Task | Resolved | 8 | 0.2 | -7.8
523127 | [RD_DEV] VFD_裝置Online/Offline資訊文件範圍確認(Config) | Rev1.14.0 DIADesigner | Task | Completed | 4 | 2.3 | -1.7
523123 | [RD_DEV] VFD_調適資訊文件範圍確認與更新_Config | Rev1.14.0 DIADesigner | Task | Resolved | 40 | 1 | -39

## WILLIAM
WILLIAM.HC.SHEN 沈桓慶
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 144.0h | 120.5h | 83.7% | 12
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583237 | [RD_DEV]ECAT 掃描更新事件 | Designer Rev1.14.0 Sprint3 | Task | Resolved | 16 | 8 | -8
582319 | [RD_DEV]DeviceEvent 寫錯導致 event 沒有觸發 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 8.5 | 0.5
577005 | [RD_DEV]W3A EtherCAT 拓樸圖從站 Advance Option 禁用 revision 檢查 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 4 | -4
577004 | [RD_DEV]ECAT PDO配置UI優化 (新增PDO, 清單畫面不要跳至第一項/ 新增PDO參數做標示) | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 14 | -2
576998 | [RD_DEV]ECAT從站客製化名稱要同步到軸上 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 10 | 2
576996 | [RD_DEV] EtherCAT ToolBar 添加 datagram 使用量 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 28 | 12
576994 | [RD_DEV]修改 ECAT 站號排列規則，從1001起 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 4 | -4
576491 | [RD_DEV][W3A] EtherCAT IO 映射表提供 sub channel 資訊給編譯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 4 | -4
576481 | [RD_DEV]新增台達裝置從裝置樹批次添加功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 12 | 12 | 0
576480 | [RD_DEV]新增總線裝置批次添加功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 12 | 12 | 0
574667 | [RD_DEV] EtherCAT_Tag_Table 變數名稱異常 | Designer Rev1.14.0 Plan | Task | Completed | 8 | 4 | -4
564806 | [RD_DEV]當使用者配置的 EtherCAT 從站項目，有超出 FECAT 或 DVP-ES3(TEC) 限制的 pdo entry數量時，跳出警告 | Designer Rev1.14.0 Plan | Task | In Progress | 24 | 12 | -12

## XAVIERA
XAVIERA.FAN 范珮欣
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 132.0h | 48.3h | 36.6% | 14
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
579571 | [RD_DEV] W3A上載新增設備時, 須初始化 Embedded Device 通訊 | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 10.5 | -13.5
579204 | [RD_DEV] VFD: online 時, 狀態列顯示錯誤 | Designer Rev1.14.0 Sprint2 | Task | Completed | 3 | 2.5 | -0.5
575221 | [RD_DEV] DVPSEC - 通訊: 上載 App Compact Bin, 固化方案版號, Program Checksum | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 1 | -3
575219 | [RD_DEV] DVPSEC - 通訊: 下載 Program Checksum 與 固化方案版號 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 0.5 | -3.5
575110 | [RD_DEV] CANopen 掃描通訊: 提供 Unknown Device 的識別資訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 3 | -5
574832 | [RD_DEV] MA500_通訊設定 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0.5 | -3.5
574831 | [RD_DEV] MA500_變頻精靈 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0.5 | -3.5
574659 | [RD_DEV] AS332EC - 通訊: 取得 Program Checksum 與 固化方案版號 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 1.6 | -6.4
574652 | [RD_DEV] AS332EC - 通訊: 下載 固化方案版號 與 Program Checksum | Designer Rev1.14.0 Sprint2 | Task | Completed | 12 | 6.1 | -5.9
574651 | [RD_DEV] AS332EC - 通訊: 上載 App Compact Bin | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 5.1 | -18.9
574005 | [RD_DEV] 通訊設定: 驗證 W3A 預設站號為 200 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.5 | -0.5
574003 | [RD_DEV] 通訊設定: 預設站號從 DDF 取得 | Designer Rev1.14.0 Sprint3 | Task | Completed | 24 | 8 | -16
521989 | [RD_DEV] DVPSEC - Embedded Corner下載管理員: Post Download | Designer Rev1.14.0 Sprint3 | Task | Resolved | 8 | 6.5 | -1.5
507452 | [RD_DEV] AS332EC - 通訊: 連線至模擬器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 4 | 2 | -2