## Summary
ESTIMATE DASHBOARD ¦ Owner Summary
Total Estimate | Total TimeSpend | Utilization Rate | Total Tasks
1838.5h | 760.0h | 41.3% | 326

## _ChartData (hidden)
Owner | Estimate(h) | TimeSpend(h) | Sprint | Estimate(h) | TimeSpend(h)
ARCHIE | 194 | 98.6 | Plan | 356 | 85.9
BORONG | 0 | 0 | Sprint1 | 60 | 34
CLONE | 158 | 86 | Sprint2 | 595 | 265.8
FRANKNC | 45 | 6 | Sprint3 | 459.5 | 220.1
JANET | 74 | 64.2 | DIADesigner | 368 | 154.2
JEAN | 128 | 31.3
JENNY | 176 | 70
JOHNNY | 308 | 4
KAKA | 60 | 6.3
MILENA | 57 | 68.6
NANCY | 275.5 | 133.1
WILLIAM | 184 | 127.5
XAVIERA | 179 | 64.4
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint2 | 4 | 15.8
[6 empty] | Sprint3 | 14 | 21.9
[6 empty] | DIADesigner | 176 | 60.9
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 97 | 40.5
[6 empty] | Sprint1 | 16 | 4.5
[6 empty] | Sprint2 | 34 | 29.5
[6 empty] | Sprint3 | 11 | 11.5
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 41 | 0
[6 empty] | DIADesigner | 4 | 6
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 10 | 9.1
[6 empty] | Sprint1 | 0 | 9.1
[6 empty] | Sprint2 | 0 | 9.6
[6 empty] | Sprint3 | 64 | 36.4
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint1 | 16 | 7.4
[6 empty] | Sprint2 | 96 | 17.7
[6 empty] | Sprint3 | 16 | 6.2
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 64 | 18
[6 empty] | Sprint1 | 2 | 2
[6 empty] | Sprint2 | 42 | 33
[6 empty] | Sprint3 | 68 | 17
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 40 | 0
[6 empty] | Sprint1 | 24 | 0
[6 empty] | Sprint2 | 208 | 0
[6 empty] | Sprint3 | 28 | 4
[6 empty] | DIADesigner | 8 | 0
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 56 | 1.3
[6 empty] | Sprint3 | 0 | 5
[6 empty] | DIADesigner | 4 | 0
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 0 | 1
[6 empty] | Sprint1 | 2 | 3
[6 empty] | Sprint2 | 16 | 28.5
[6 empty] | Sprint3 | 32 | 7.6
[6 empty] | DIADesigner | 7 | 28.5
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint2 | 16 | 15.8
[6 empty] | Sprint3 | 90.5 | 58.5
[6 empty] | DIADesigner | 169 | 58.8
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Plan | 48 | 16
[6 empty] | Sprint1 | 0 | 2
[6 empty] | Sprint2 | 100 | 85
[6 empty] | Sprint3 | 36 | 24.5
[6 empty] | Sprint | Estimate(h) | TimeSpend(h)
[6 empty] | Sprint1 | 0 | 6
[6 empty] | Sprint2 | 79 | 30.9
[6 empty] | Sprint3 | 100 | 27.5

## ARCHIE
ARCHIE.YANG 楊浩群
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 194.0h | 98.6h | 50.8% | 39
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583575 | [RD_DEV] 新增 DIO 調機 Icon | Designer Rev1.14.0 Sprint3 | Task | Completed | 0.5 | 0.1 | -0.4
583543 | [RD_DEV] 開啟通訊設定視窗時更新專案樹呈現的裝置連線狀況 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.4 | -0.6
583532 | [RD_DEV] 新增不做資料處理的 ModbusProtocolBase，新增可自訂 IConnector 的 Ethernet 設定物件 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 3.3 | -0.7
583509 | [RD_DEV] ETH 通訊設定改用統一的 Element Name 儲存 | Designer Rev1.14.0 Sprint3 | Task | Completed | 2 | 1.9 | -0.1
583499 | [RD_DEV] 調整 ASD Run/Stop 狀態訊息為 Servo On/Off | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.8 | -0.2
582453 | [RD_DEV] 修正建立上下載項目的最上層過濾條件 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.6 | 0.6
582291 | [RD_DEV] VFD Monitor Table 釋放時需先關閉頁籤再釋放底層物件 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.8 | -0.2
582128 | [RD_DEV] 支援ASD A3-EX功能_DDF Model 新增，Port-X > Item-X 新增 ProtocolType HLLT | Designer Rev1.14.0 Sprint3 | Task | Completed | 0.5 | 0.2 | -0.3
581412 | [RD_DEV] W3A 下載管理員內資料交換表與參數編輯器項目新增同步邏輯 | Rev1.14.0 DIADesigner | Task | Completed | 2 | 1.5 | -0.5
581137 | [RD_DEV] PLC 支援取消上載、下載並等待結束 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 10.7 | 10.7
581118 | [RD_DEV] W3A 上下載管理員使用模擬器時禁止勾選參數編輯器項目 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.7 | -0.3
580409 | [RD_DEV] VFD CSV, XLSX 參數匯出不把空白的 Unit 輸出成 '#' | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 1.5 | -0.5
579941 | [RD_DEV] 修正 DVP Scan 未還原整合 DIO 模組的問題 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1 | 0
579812 | [RD_DEV] DVP 改用 ProdSubseries 判斷還原整合 DIO 模組 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
579798 | [RD_DEV] 修正 ASD 在上載管理員消失的問題 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 1 | 0
579586 | [RD_DEV] W3A 連線時的驗證結果需保存 | Rev1.14.0 DIADesigner | Task | Completed | 0.5 | 0.5 | 0
579528 | [RD_DEV] 修正上載管理員內加入新裝置時沒有顯示節點 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 0.5 | -0.5
579337 | [RD_DEV] 新增 A3-EP 的 Device ID Code | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.5 | -0.5
579293 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Asd.*) | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.5 | 0.5
579026 | [RD_DEV] 更新 SDK Style (DeltaIA.DIAStudio.Corner.Communication) | Rev1.14.0 DIADesigner | Task | Completed | 0.5 | 0.8 | 0.3
578950 | [RD_DEV] TC 支援取消上載、下載並等待結束 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 4.1 | 4.1
578719 | [RD_DEV] 修正 TC 無法下載的問題 (Check 失敗) | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1 | 0
578701 | [RD_DEV] ASD/Corner 支援取消上載、下載並等待結束 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 5.1 | 5.1
578693 | [RD_DEV] 改善上下載管理員效能 (ASD、VFD 有大量參數節點時) | Rev1.14.0 DIADesigner | Task | Completed | 3 | 5 | 2
577354 | [RD_DEV] 修正 SetupDiGetClassDevs 回傳值的判斷方式 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.5 | -0.5
577139 | [RD_DEV] 支援無配置時以預設行為初始化 CommgrHelper | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.7 | -0.3
577137 | [RD_DEV] 修正判斷 ASDASoft Process 的邏輯，避免問錯對象，反覆發生例外 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 0.7 | -0.3
577088 | [RD_DEV] W3A 增加 Servo 參數編輯器與上下載項目 | Rev1.14.0 DIADesigner | Task | Completed | 6 | 8 | 2
576366 | [RD_DEV] 刪除 ASD 裝置時應正確釋放參數編輯器 | Rev1.14.0 DIADesigner | Task | Completed | 2 | 2 | 0
576006 | [RD_DEV] 調整 MODBUS 接收資料的預設 Delay 為 0 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.5 | 0.5
575926 | [RD_DEV] VFD 支援取消上載、下載並等待結束 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 3.6 | 3.6
573068 | [RD_DEV] 架構圖更新 (Commission part) - DIADesigner v1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
573063 | [RD_DEV] 架構圖更新 (HW part) - DIADesigner v1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
569952 | [RD_DEV] DVP16SV3 HW存讀檔需容舊型號 | Designer Rev1.14.0 Sprint3 | Task | Completed | 3 | 3 | 0
527017 | [RD_DEV][W3A]通訊參數設定-下載通訊相關參數 | Rev1.14.0 DIADesigner | Task | Completed | 40 | 19 | -21
527016 | [RD_DEV][W3A]通訊參數設定-上載通訊相關參數 | Rev1.14.0 DIADesigner | Task | Completed | 40 | 12.1 | -27.9
505160 | [RD_DEV] 調整 PLC 主機下載流程，優先下載 CANopen 參數，第一階段 | Rev1.14.0 DIADesigner | Task | Assigned | 24 | 0 | -24
505153 | [RD_DEV] 從 Model 建立 PLC 參數，優化效能 | Rev1.14.0 DIADesigner | Task | Assigned | 24 | 0 | -24
484525 | [RD_DEV] ADC客製案_Architecture Design_採用注入方式 | Rev1.14.0 DIADesigner | Task | In Progress | 24 | 2 | -22

## BORONG
BORONG.CHEN 陳柏融
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 0.0h | 0.0h | — | 4
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
582568 | DIADesigner source code permission application from MDSBU 陳贊宇 | Rev1.14.0 DIADesigner | Task | Completed | 0 | 0 | 0
579534 | DIADesigner source code permission application from MOK | Rev1.14.0 DIADesigner | Task | Completed | 0 | 0 | 0
572578 | Project Summary: DIADesigner Rev1.14.0 | Rev1.14.0 DIADesigner | Task | In Progress | 0 | 0 | 0
546027 | [RD_DEV] IEC 62443-4-1 合規 (Part1)_DM checklist_Rational - Product Dashboard | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0

## CLONE
CLONE.LIN 林俊淵
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 158.0h | 86.0h | 54.4% | 28
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583940 | [RD_DEV] 網路視圖在特定操作下刪除總線網路會發生線段殘留現象 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
580772 | [RD_DEV] AS332EC - NW支援雙網孔 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 4.5 | 4.5
577484 | [RD_DEV] APF3000_網路視圖 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 2.5 | 0.5
577472 | [RD_DEV] VA3000_網路視圖 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1.5 | 1.5
577069 | [RD_DEV] (網路配置)网络视图，拖拽链接时，不应该自动修改通讯地址，建议增加跳转可编辑选项 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 16 | 0
575993 | (Cyber Security) Regular review process of Main Process | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1.5 | 0.5
575864 | (Cyber Security) Regular review process of General Review Process | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
574837 | [RD_DEV] MA500_網路視圖 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0 | -1
574821 | [RD_DEV] APF3000_網路視圖 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 0 | 0 | 0
573571 | [RD_DEV] HMI NW | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 9.5 | -6.5
573064 | [RD_DEV] 架構圖更新 (NW part) - DIADesigner v1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
562190 | [RD_DEV] 若轉換成 AS300 系列，且有配置 CANopen 時，需自動配置 AS-FCOPM 卡 | Designer Rev1.14.0 Plan | Task | Assigned | 16 | 0 | -16
562185 | [RD_DEV] 通訊參數皆需保留 (Modbus, ModbusTcp, EIP, CANopen) | Designer Rev1.14.0 Plan | Task | Assigned | 16 | 0 | -16
546040 | [RD_DEV] IEC 62443-4-1 合規 (Part1)_Conformity of DM-1 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
546033 | (Cyber Security) Regular review process of Development Master Record | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
546032 | (Cyber Security) Regular review process of SBOM Process | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
546013 | [RD_DEV] IEC 62443-4-1 合規 (Part1)_TMRA Report (CSRS) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
525119 | [RD_DEV] AS332EC - 設備主體: 無法執行 PLC EIP Scan 功能 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 1 | 0
522702 | [RD_DEV] DVPSEC - Check NW PC Scan 是否可找到 DVPSEC | Designer Rev1.14.0 Sprint3 | Task | Completed | 2 | 2 | 0
522701 | [RD_DEV] DVPSEC - Check NW 是否可執行PLC EIP Scan功能 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0.5 | -3.5
518208 | [RD_DEV] 其它-模擬器 | Designer Rev1.14.0 Plan | Task | Completed | 1 | 0 | -1
518202 | [RD_DEV] IO-Link Device 監控頁面 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 0 | 0
518201 | [RD_DEV] IO-Link Master 監控頁面 | Designer Rev1.14.0 Plan | Task | Completed | 16 | 16.5 | 0.5
518200 | [RD_DEV] IO-Link 監控頁面的主畫面 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 0 | 0
518199 | [RD_DEV] IO-Link 監控頁面 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 0 | 0
518196 | [RD_DEV] IO-Link Master 設定頁面 - Process Data 分頁 | Designer Rev1.14.0 Plan | Task | Completed | 32 | 24 | -8
518186 | [RD_DEV] 全域工具列-監控 IO-Link 資訊 | Designer Rev1.14.0 Plan | Task | Completed | 16 | 0 | -16
507752 | [RD_DEV] DIADesigner shall be able to download/upload via the AS-FFTP01 card | Designer Rev1.14.0 Sprint1 | Task | Completed | 16 | 4.5 | -11.5

## FRANKNC
FRANKNC.HO 何南瑾
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 45.0h | 6.0h | 13.3% | 11
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
579119 | [RD_DEV] 資料交換表顯示連線數 | Rev1.14.0 DIADesigner | Task | Completed | 0 | 2 | 2
577622 | [RD_DEV] DVP16SV3_網路視圖 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 0 | 0 | 0
576410 | [RD_DEV]匯出 | Rev1.14.0 DIADesigner | Task | Completed | 0 | 0 | 0
576409 | [RD_DEV]匯入不支援的Modbustcp版本或是不相同的Field Bus要防呆 | Rev1.14.0 DIADesigner | Task | Completed | 4 | 4 | 0
575138 | [RD_DEV]匯入 | Rev1.14.0 DIADesigner | Task | Completed | 0 | 0 | 0
575111 | [RD_DEV] CANopen 掃描結果: Unknwon Device 呈現於掃描結果列表 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
562187 | [RD_DEV] 資料交換表的從站裝置支援上限檢查 (EIP, CANopen) | Designer Rev1.14.0 Plan | Task | Assigned | 0 | 0 | 0
562186 | [RD_DEV] 資料交換表的主站暫存器支援範圍檢查 (Modbus, ModbusTcp, EIP, CANopen) | Designer Rev1.14.0 Plan | Task | Assigned | 0 | 0 | 0
518204 | [RD_DEV] 符號表-IO-Link Tag Table | Designer Rev1.14.0 Plan | Task | Completed | 1 | 0 | -1
518203 | [RD_DEV] 符號表-IO-Link I/O Mapping | Designer Rev1.14.0 Plan | Task | Rejected | 40 | 0 | -40
518198 | [RD_DEV] IO-Link Device 設定頁面 - Process Data 分頁 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 0 | 0

## JANET
JANET.JC.CHEN 陳美蓁
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 74.0h | 64.2h | 86.8% | 25
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583872 | [RD_DEV](上下載管理員)加入HMI裝置後，上下載管理員無法開啟&開始傳輸按鈕邏輯修正 | Designer Rev1.14.0 Sprint3 | Task | Resolved | 0 | 0 | 0
583294 | [RD_DEV](硬體配置) RTU 使用LC校正精靈沒接外部電源時，上下載會出現通訊錯誤的訊息，需優化提示訊息 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 3.2 | 3.2
583232 | [RD_DEV](專案管理) 當專案存檔路徑為網路路徑且無存讀權限時， 軟體被拒絕後就會crash(無法操作) | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 2.1 | 2.1
581144 | [RD_DEV](上載管理員) 裝置勾選三態修正 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 3.6 | 3.6
580591 | (硬體配置) DVP16SEC裝置資訊例外 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
579664 | [RD_DEV](上下載管理員) 父節點CheckStatus判斷修正、裝置節點預設Enable | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 9.5 | 9.5
579553 | [RD_DEV] APF3000_硬體配置通訊卡參數修正 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
579040 | [RD_DEV]機種切換會發生例外 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 2.1 | 2.1
578934 | [RD_DEV](專案管理) [KA]硬件组态删除无法撤销；功能块或者程序块删除无法撤销 (改為跳提示訊息告知無法回復，且用戶可勾不再提示。) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
577618 | [RD_DEV] DVP16SV3_硬體配置 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 1 | 1
577479 | [RD_DEV] APF3000_硬體配置 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0.5 | 0.5
577477 | [RD_DEV](下載管理員)EtherCAT、軸、E-CAM勾選連動與勾選三態修正 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 7 | 7
577469 | [RD_DEV] VA3000_硬體配置 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 2 | 2
577108 | [RD_DEV] 研究Black Duck工具與分析掃描報告 | Designer Rev1.14.0 Sprint3 | Task | In Progress | 40 | 0 | -40
576020 | [RD_DEV](專案管理) AS 機種專案下載節點訊息顯示內容不符預期 | Designer Rev1.14.0 Plan | Task | Completed | 0 | 2.1 | 2.1
575705 | (Cyber Security) Regular review process of TMRA Process | Designer Rev1.14.0 Sprint3 | Task | Completed | 24 | 10 | -14
575089 | [RD_DEV](硬體配置) DVP16SEC上載管理員配置出現錯誤子項目 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 9.1 | 9.1
574835 | [RD_DEV] MA500_上下載 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
574833 | [RD_DEV] MA500_硬體配置 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
574819 | [RD_DEV] APF3000_上下載 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 0 | 0 | 0
574817 | [RD_DEV] APF3000_硬體配置 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 0 | 0 | 0
573099 | (Cyber Security) Regular review process of Configuration Items | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 7 | 7
562193 | [RD_DEV] 當移除 DVP-EN02 配置時，轉換前需提示訊息，告知 DVP-EN02 配置及相關資料交換將被刪除 | Designer Rev1.14.0 Plan | Task | Assigned | 5 | 0 | -5
562192 | [RD_DEV] 當移除 EIP RTU 配置時，轉換前需提示訊息，告知 RTU 配置及相關資料交換將被刪除 | Designer Rev1.14.0 Plan | Task | Assigned | 5 | 0 | -5
546029 | (Cyber Security) Regular review process of Single Develop Task Process | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 5 | 5

## JEAN
JEAN.LC.WANG 王儷臻
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 128.0h | 31.3h | 24.5% | 48
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583009 | [PLM] PJ134A-26-SS3-4-2-02-12_SE-SDD II (Detail Design)(4-2 SE-SDDD) | Designer Rev1.14.0 Sprint3 | Task | Resolved | 0 | 2 | 2
581324 | [RD_DEV] 驗證AS300EC 硬體配置通訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
580022 | [RD_DEV] DVP16SV3_Online/Offline Status Bar | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
580015 | [RD_DEV] HMI 機種轉換 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
579914 | [RD_DEV] 組態上載後更新實際值到輸入值欄位 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
579532 | [RD_DEV] HMI 存讀檔 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
578419 | [RD_DEV][W3A] HW_Tag_Table 新增按鈕更新以DDF內容為主產生系統變數的功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
578273 | [PLM] PJ134A-26-SS3-3-2-05_SE_SRS (Software) (3-2 SRS(Software)) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
578013 | [RD_DEV][W3A] IOMap Subitem 的變數位址調整 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
578011 | RD/TE--軟體架構圖更新--同步DDF & DLL給DIASelector | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
577931 | [RD_DEV] HMI 專案樹節點右鍵開啟DIAScreen | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
577617 | [RD_DEV] DVP16SV3_通訊設定 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
577616 | [RD_DEV] DVP16SV3_新增裝置 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
577357 | [RD_DEV][W3A]若存檔格式有調整舊軟體不能開新版存檔內容 | Designer Rev1.14.0 Sprint2 | Task | Resolved | 0 | 0.1 | 0.1
576859 | [RD_DEV] DVP 三代機 正確新增左右側模組 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 0 | 0
576777 | 在DIADesigner的拓樸圖可加入HMI (的圖示)，用於專案前期對客戶說明規畫 (規格文件) | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
576618 | [RD_DEV] DVP 三代機模擬器連線 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 0 | 0
576598 | [RD_DEV] DVP 三代機模組清單 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 0 | 0
576490 | [RD_DEV][W3A] Local IO 映射表提供 sub channel 資訊給編譯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 1 | 1
576489 | [RD_DEV][W3A] Motion interface IO 映射表提供 sub channel 資訊給編譯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 1 | 1
573569 | [RD_DEV] HMI在軟體上工具列上通用功能的皆須防呆不可操作 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0.1 | 0.1
573567 | [RD_DEV] 新增 HMI 機種 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
573304 | [RD_DEV] DVPSEC - 驗證 硬體配置連線功能 | Designer Rev1.14.0 Sprint3 | Task | In Progress | 0 | 2.2 | 2.2
572907 | [PLM] PJ116A-MS300-NEMA4X-DB, PJ116A-MS300-NEMA4X-D - 3-2-05_SE_SRS (Software) (3-2 SRS(Software)) | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 2 | 2
572752 | [RD_DEV] 初步驗證 B5 下載 | Designer Rev1.14.0 Sprint1 | Task | In Progress | 16 | 2 | -14
572033 | [RD_DEV][W3A] RefreshIndexTool Corner Mode | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1.5 | 1.5
569945 | [RD_DEV] DVP16SV3 機種變更清單 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 0 | 0
569336 | [RD_DEV] (新增裝置)(工程版)支援ASD-B5 - 規格文件 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 0 | 0 | 0
566580 | [RD_DEV] 組態上載 封包間間隔時間略長 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
566578 | [RD_DEV] 詢問是否上載子選單細項內容 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
566576 | [RD_DEV] 支援 MX 逆變軸組態上載 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 0 | 0
566575 | [RD_DEV]支援 MX 整流組態上載 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 0.2 | 0.2
565887 | [RD_DEV] 支援 GV50的Eth組態上載 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 3.2 | 3.2
565106 | [RD_DEV] VP-E/EHS 支援組態上載前的語系切換功能 | Designer Rev1.14.0 Sprint1 | Task | In Progress | 0 | 0 | 0
565103 | [RD_DEV] VP-E/EHS 高速組態上載 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 0 | 0 | 0
562057 | [RD_DEV] AS332EC - ASDEV DDF 紀錄固化方案版本 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
552362 | [RD_DEV][W3A] HW裝置比對 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 0 | 0 | 0
550865 | [RD_DEV][W3A] - 通訊: Online - 使用實機, 取得 ASD 設備狀態 | Designer Rev1.14.0 Sprint3 | Task | Completed | 16 | 0 | -16
550860 | [RD_DEV][W3A] HW - Online前比對取得 Checksum, 使用 Corner Communication | Designer Rev1.14.0 Sprint2 | Task | In Progress | 0 | 0 | 0
549498 | [RD_DEV][W3A] update W3A DDF | Designer Rev1.14.0 Sprint2 | Task | In Progress | 16 | 0 | -16
542232 | [RD_DEV] 支援 GV50的高速組態上載 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 0 | 0 | 0
527352 | [RD_DEV][W3A] - Corner 參數編輯器 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 0 | 0 | 0
527350 | [RD_DEV][W3A] - 伺服參數編輯器數值讀寫 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 0 | 0 | 0
527347 | [RD_DEV][W3A] - 伺服參數編輯器 畫面與項目 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 0 | 0 | 0
525431 | [RD_DEV][W3A] - 產品包驗證 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 8 | 2 | -6
525174 | [RD_DEV] AS332EC - Embedded Corner: 固化方案 - 更新機制的相容性 | Designer Rev1.14.0 Sprint2 | Task | Completed | 40 | 0 | -40
521966 | [RD_DEV] DVPSEC - 產品包驗證 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 16 | 0 | -16
499614 | [RD_DEV] AS332EC - Corner 產品包驗證 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 16 | 14 | -2

## JENNY
JENNY.HY.CHEN 陳湘筠
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 176.0h | 70.0h | 39.8% | 32
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
582732 | [RD_DEV] MX300 keypad 取值失敗時不應清空數值及單位 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 3 | -1
581076 | [RD_DEV][W3A] 擴充 0x48 錯誤訊息多國語系 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 6 | -2
581075 | [RD_DEV][W3A] 擴充 0x48 sfc3 封包格式 | Designer Rev1.14.0 Sprint3 | Task | Completed | 12 | 8 | -4
579545 | [RD_DEV][W3A] 示波器簡化PLC位置不合法錯誤資訊 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 1 | 0
578176 | [RD_DEV][W3A] 使用 W3A 模擬器連線示波器的情況下，監控項目若有 Servo Normal 則要跳警告視窗 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 3 | 1
578175 | [RD_DEV][W3A] 示波器監測項目為零的警告視窗增加易讀描述 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 1 | -1
578174 | [RD_DEV][W3A] 進入多頻道模式時，應禁用各自座標系 | Designer Rev1.14.0 Sprint2 | Task | Completed | 1 | 1 | 0
578171 | [RD_DEV][W3A] 多通道示波器監控時，多通道 Y 軸沒有自動調整範圍 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 2 | 0
577486 | [RD_DEV] APF3000_示波器 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
577473 | [RD_DEV] VA3000_示波器 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
576755 | [RD_DEV] 示波器停用動畫功能以提升效能，減少不必要運算 | Designer Rev1.14.0 Sprint1 | Task | Completed | 2 | 2 | 0
576749 | [RD_DEV] ASD 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 0 | -2
576748 | [RD_DEV] PLC logger & Tracer 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 2 | 0
576747 | [RD_DEV][W3A] W3A 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 10 | 2
576746 | [RD_DEV] VFD 示波器加入 undo/redo 功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 2 | -2
576740 | [RD_DEV][W3A] 多畫布加入 visibleRange 變更事件 | Designer Rev1.14.0 Sprint2 | Task | Completed | 2 | 1 | -1
575846 | [RD_DEV][W3A] 示波器增加最小、最大、平均值顯示欄位 | Designer Rev1.14.0 Plan | Task | Completed | 8 | 2 | -6
574840 | [RD_DEV] MA500_通訊測試工具 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 1 | -3
574839 | [RD_DEV] MA500_示波器 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 1 | -7
574838 | [RD_DEV] MA500_數位操作器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 2 | -2
574826 | [RD_DEV] APF3000_通訊測試工具 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 4 | 0 | -4
574823 | [RD_DEV] APF3000_示波器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8
574822 | [RD_DEV] APF3000_數位操作器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 4 | 0 | -4
574221 | [RD_DEV] W3A 多節點示波器 (1.14) | Designer Rev1.14.0 Plan | Task | Assigned | 0 | 0 | 0
573066 | [RD_DEV] 架構圖更新 (Oscilloscope part) - DIADesigner v1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
570316 | [RD_DEV][W3A] 示波器停止時最小、最大、平均值隨畫面範圍內的數值變化 | Designer Rev1.14.0 Plan | Task | Completed | 16 | 6 | -10
540114 | [RD_DEV][W3A] 示波器導入VFD示波器的事件觸發功能 | Designer Rev1.14.0 Plan | Task | In Progress | 16 | 10 | -6
528310 | [RD_DEV] 調機精靈_Development_示波器相關功能_波形存檔 | Designer Rev1.14.0 Plan | Task | In Progress | 24 | 0 | -24
526437 | [RD_DEV][W3A] Corner 示波器各CH獨立頻寬操作 - 配合機種DDF來呈現取樣頻率清單 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 4 | 0
505453 | [RD_DEV] VA3000_通訊測試工具 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8
505451 | [RD_DEV] VA3000_示波器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8
505449 | [RD_DEV] VA3000_數位操作器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8

## JOHNNY
JOHNNY.MC.YEH 葉明勳
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 308.0h | 4.0h | 1.3% | 18
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
580402 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 Monitor 選項 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 0 | -16
580401 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 Adress 選項 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 0 | -16
580400 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 CANopen 選項 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 0 | -16
580235 | [JIRA] (調適) [IABGVOC-1705] 示波器 Monitor Type 導入A2架構的 Parameter 選項 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 0 | -16
578133 | [RD_DEV] AS332EC - 下載管理員: 下載 App Compact Bin 修改觸發時間點 | Designer Rev1.14.0 Sprint2 | Task | In Progress | 24 | 0 | -24
577623 | [RD_DEV] DVP16SV3_示波器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 4 | 0
576932 | [RD_DEV] AS332EC - 下載管理員: 下載 App Compact Bin 時, 須帶入 Program Checksum | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 0 | -24
575269 | [RD_DEV] ASD_DLL權限申請與驗證 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 0 | -8
575205 | [RD_DEV](B5 Oscilloscope)ASD_DLL COM Port API串接 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 40 | 0 | -40
575198 | [RD_DEV] B5 專案下載韌體除錯 | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 0 | -24
575176 | [RD_DEV] DVPSEC - 上載管理員: 觸發上載 App Compact Bin | Rev1.14.0 DIADesigner | Task | Completed | 8 | 0 | -8
575175 | [RD_DEV] AS332EC -上載管理員: 觸發上載 App Compact Bin | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 0 | -24
574225 | [RD_DEV] W3A 多節點示波器 - Pool - 建立資料池 | Designer Rev1.14.0 Sprint1 | Task | Completed | 24 | 0 | -24
574224 | [RD_DEV] W3A 多節點示波器 - Pool (1.14) | Designer Rev1.14.0 Plan | Task | Completed | 40 | 0 | -40
572839 | [RD_DEV] AS332EC - 設備主體: 上載管理員 - 上載 Project Compact Bin 前, 取消比對 Checksum | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 0 | -8
565510 | VFD MNTR 示波器及組態上載規格整理(serial, ethernet) | Rev1.14.0 DIADesigner | Task | Completed | 0 | 0 | 0
521974 | [RD_DEV] DVPSEC - 模擬器不支援功能 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8
507066 | [RD_DEV] AS332EC - 模擬器不支援功能 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8

## KAKA
KAKA.WU 吳思言
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 60.0h | 6.3h | 10.5% | 8
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
584033 | [RD-DEV][For Config team](專案管理) icon灰色时,鼠标移至，也可显示提示 | Designer Rev1.14.0 Sprint3 | Task | Resolved | 0 | 2 | 2
583901 | [RD-DEV][JIRA] (調適) [IABGVOC-1685] 示波器工具列圖示調整 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 2 | 2
583762 | [RD-DEV](專案管理)更換匯出匯入ICON | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 1 | 1
581079 | [RD-DEV] [JIRA] (程式編輯) [IABGVOC-2013] 及時刷新 LOG 狀態下關閉頁籤，在线仿真發生例外 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
576791 | (專案管理) 主工具列新增自定義喜好按钮 (規格文件) | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
574793 | [RD_DEV]更新多國語系_1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 4 | 0 | -4
573067 | [RD_DEV] 架構圖更新 (UI part) - DIADesigner v1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
518197 | [RD_DEV] IO-Link Device 設定頁面 - Parameter 分頁 | Designer Rev1.14.0 Plan | Task | Completed | 56 | 1.3 | -54.7

## MILENA
MILENA.CHEN 陳孟歆
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 57.0h | 68.6h | 120.4% | 34
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583357 | [RD_DEV] (DDF)W3A DDF示波器功能新增軸號區段與相關屬性 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 1.5 | 1.5
583212 | [RD_DEV] AS00SCM-A 新增參數，更新 DDF | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
582518 | [RD_DEV] 修正 Corner 下載管理員 IsCompiled 判定邏輯 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 2 | 2
582127 | [RD_DEV] 支援ASD A3-EX功能_DDF 規格新增，Port-X > Item-X 新增 ProtocolType HLLT | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0.5 | 0.5
581875 | [RD_DEV] 通訊設定: W3A 修改 DDF 中各通訊介面的預設站號 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0.6 | 0.6
580709 | [RD_DEV] Migrate DdfCheck from DIAOneWeb.WebAPI to DIADesigner | Rev1.14.0 DIADesigner | Task | Completed | 4 | 4 | 0
579662 | [RD_DEV] 無裝置圖片時使用預設圖片 (ASD/HMI/VFD) | Rev1.14.0 DIADesigner | Task | Completed | 0 | 2.5 | 2.5
578957 | [RD_DEV] 修正寫 Device.xml Document NodeType 行為 | Rev1.14.0 DIADesigner | Task | Completed | 2 | 2 | 0
578750 | [RD_DEV]支援ASD A3-EX功能 POC_DDF | Designer Rev1.14.0 Sprint3 | Task | In Progress | 8 | 0.5 | -7.5
578277 | [PLM] PJ126A-25D301 - 3-2-05_SE_SRS (Software) (3-2 SRS(Software)) | Rev1.14.0 DIADesigner | Task | Completed | 0 | 1 | 1
577620 | [RD_DEV] DVP16SV3_裝置與錯誤資訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 0.5 | -7.5
577482 | [RD_DEV] APF3000_裝置與錯誤資訊 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
577471 | [RD_DEV] VA3000_裝置與錯誤資訊 (離線功能) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
577405 | [RD_DEV] W3A IQM Modbus Mapping_下載前編譯檢查 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 2 | 2
577284 | [RD_DEV] 調整 Device Import 選擇資料夾 UI | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 6 | 6
576891 | [RD_DEV] Modbus Address Mapping 編譯錯誤後點擊錯誤訊息跳轉到對應畫面 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 2 | 2
576375 | [RD_DEV] MX300 DDF Update to V1.03 (更新版本) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
576346 | [RD_DEV] ASD A3-M 新增 DDF (新機種) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
576345 | [RD_DEV] ASD B3-M 新增 DDF (新機種) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
576331 | [RD_DEV] ASD-A3-M 220V DDF Update (無版本更新) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0 | 0
576260 | [RD_DEV] ASD-B3-M 220V DDF Update (無版本更新) | Designer Rev1.14.0 Plan | Task | Completed | 0 | 1 | 1
576256 | (Cyber Security) Document clarify - Main Process | Rev1.14.0 DIADesigner | Task | Completed | 0 | 2 | 2
574836 | [RD_DEV] MA500_裝置與錯誤資訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 2 | -2
574830 | [RD_DEV] MA500_新增裝置 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 1 | -3
574829 | [RD_DEV] MA500_DDF (新機種) | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 1 | -7
574813 | [RD_DEV] APF3000_新增裝置 & DDF/EDS (release 前移除) | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 1 | -3
574786 | [RD_DEV] MX300-S_新增裝置 & DDF (新機種) | Designer Rev1.14.0 Sprint1 | Task | Completed | 2 | 1 | -1
573572 | [RD_DEV] HMI 圖檔 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 9.5 | 1.5
573565 | [RD_DEV] 確認支援HMI機種與DDF (無版本更新) | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
573547 | [RD_DEV] IABG Specification_DIADesigner 功能總表進版 | Rev1.14.0 DIADesigner | Task | Completed | 0 | 9 | 9
573433 | [RD_DEV] IABG Specification_DDF Spec 轉移成 Confluence Page | Rev1.14.0 DIADesigner | Task | Completed | 0 | 8 | 8
571837 | [RD_DEV] DDF & EDS index files version refresh (for DIADesigner 1.14.0) | Rev1.14.0 DIADesigner | Task | Assigned | 1 | 0 | -1
569944 | [RD_DEV] 更新 DVP 更換系列的DDF (調整系列名) | Designer Rev1.14.0 Sprint3 | Task | In Progress | 0 | 0 | 0
505435 | [RD_DEV] VA3000_新增裝置 & DDF (release 前移除) | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 3 | -1

## NANCY
NANCY.TC.YANG 楊采真
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 275.5h | 133.1h | 48.3% | 26
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583893 | [RD_DEV](網路配置) 網路通訊總線變更名稱後會殘留舊名稱的總線網路 | Rev1.14.0 DIADesigner | Task | Resolved | 0 | 0 | 0
583760 | [RD_DEV](網路配置) 未開啟網路視圖時先新增裝置再開啟網路視圖建立Modbus連線後其總線的網路參數連動功能行為異常 | Rev1.14.0 DIADesigner | Task | Completed | 0 | 0 | 0
580791 | [RD_DEV] (硬體配置) AS300EC 機種從硬體配置新增功能卡會出現Exception | Rev1.14.0 DIADesigner | Task | Completed | 8 | 8.5 | 0.5
580454 | [RD_DEV](硬體配置) 取消轉送設定後開啟網路視圖參數設定被竄改 | Rev1.14.0 DIADesigner | Task | Deferred | 0 | 0 | 0
580436 | [RD_DEV] (硬體配置) 取消轉送設定後開啟網路視圖參數設定被竄改 | Rev1.14.0 DIADesigner | Task | Completed | 8 | 6 | -2
578818 | [RD_DEV][JIRA] (專案管理) [IABGVOC-1786] DIADesigner专案名字有写小数点的版本号时，如果另外档案，目前会把最后一个小数点的数值删除掉 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 3.5 | -0.5
578350 | [RD_DEV]支援ASD A3-EX功能 POC_Online/Offline_SRS | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 5.5 | 1.5
578140 | [RD_DEV]支援ASD A3-EX功能 POC_DI DO function configuration Requirement_SRS | Designer Rev1.14.0 Sprint3 | Task | Resolved | 12 | 11.5 | -0.5
578123 | [RD_DEV](線上模式) 線上模式匹配不符時， 英文的提示字會被切掉 | Rev1.14.0 DIADesigner | Task | Completed | 1 | 1.7 | 0.7
578070 | [RD_DEV](新增裝置) When clicking a node in the project tree with the mouse, the focused item does not display a colored background. (3/3) | Rev1.14.0 DIADesigner | Task | Completed | 4 | 2.1 | -1.9
577958 | [RD_DEV]支援ASD A3-EX功能 POC_Ethernet Connection Requirement_SRS | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 1.5 | -6.5
577777 | [RD_DEV](網路配置) 项目树与网络视图控制，联动，可同时选中 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 4.1 | 0.1
577624 | [RD_DEV] DVP16SV3_機種轉換 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0.5 | 0.5 | 0
577619 | [RD_DEV] DVP16SV3_參數編輯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 2 | 1.5 | -0.5
576903 | [RD_DEV](專案管理) 當任一裝置切換成線上模式時，DIADesigner 應一律禁止上載下載行為 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 8.2 | 0.2
576235 | [RD_DEV]DURApulse Designer 2st Beta SW Review Reply_20260413 | Designer Rev1.14.0 Sprint3 | Task | Completed | 32 | 17.5 | -14.5
576071 | [RD_DEV] 規劃如何讓Security Main Process運行在既有Designer版本流程上 | Designer Rev1.14.0 Sprint3 | Task | In Progress | 24 | 18 | -6
575782 | [RD_DEV]DURApulse Designer 2st Beta SW Review Reply_20260409 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
574834 | [RD_DEV] MA500_參數編輯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 2.5 | -5.5
572194 | [RD_DEV] 1.14.0 PJM & PMO Related work | Rev1.14.0 DIADesigner | Task | In Progress | 40 | 20 | -20
560174 | [RD_DEV] 修改VFD SRS Template內容 | Rev1.14.0 DIADesigner | Task | In Progress | 0 | 0 | 0
560172 | [RD_DEV] 修改SAS內容 | Rev1.14.0 DIADesigner | Task | Completed | 40 | 5 | -35
558807 | [RD_DEV] 申請表併入SAS、參數對應表、SRS等文件 | Rev1.14.0 DIADesigner | Task | Completed | 16 | 12 | -4
532083 | [RD_DEV] VFD_資料交換表文件範圍確認與更新 | Rev1.14.0 DIADesigner | Task | Resolved | 8 | 0.2 | -7.8
523127 | [RD_DEV] VFD_裝置Online/Offline資訊文件範圍確認(Config) | Rev1.14.0 DIADesigner | Task | Completed | 4 | 2.3 | -1.7
523123 | [RD_DEV] VFD_調適資訊文件範圍確認與更新_Config | Rev1.14.0 DIADesigner | Task | Resolved | 40 | 1 | -39

## WILLIAM
WILLIAM.HC.SHEN 沈桓慶
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 184.0h | 127.5h | 69.3% | 25
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
583237 | [RD_DEV]ECAT 掃描更新事件 | Designer Rev1.14.0 Sprint3 | Task | Resolved | 16 | 8 | -8
582319 | [RD_DEV]DeviceEvent 寫錯導致 event 沒有觸發 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 8.5 | 0.5
582229 | [RD_DEV] AS300EC 與 DVP-SEC 要處理 ECAT 與 IO 映射連動 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
581242 | [RD_DEV]EtherCAT ESI String Type 預設值為空值 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0 | -4
577848 | [RD_DEV]Form InitCmd 建立與預設參數相同的項目時，建立方式錯誤 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 4 | 4
577179 | [RD_DEV]Corner 通訊 dll 和 ECAT 解耦 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1 | 1
577005 | [RD_DEV]W3A EtherCAT 拓樸圖從站 Advance Option 禁用 revision 檢查 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 4 | -4
577004 | [RD_DEV]ECAT PDO配置UI優化 (新增PDO, 清單畫面不要跳至第一項/ 新增PDO參數做標示) | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 14 | -2
577001 | [RD_DEV]排除 W3A EtherCAT 停用導致編譯卡住的問題 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 0 | -8
576999 | [RD_DEV]修改 EtherCAT 專案，儲存使用的檔案名稱 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 0 | -8
576998 | [RD_DEV]ECAT從站客製化名稱要同步到軸上 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 10 | 2
576996 | [RD_DEV] EtherCAT ToolBar 添加 datagram 使用量 | Designer Rev1.14.0 Sprint2 | Task | Completed | 16 | 28 | 12
576994 | [RD_DEV]修改 ECAT 站號排列規則，從1001起 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 4 | -4
576993 | [RD_DEV]W3A ECAT 存檔造成到 Primary Task 間隔時間被改成 2ms | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 0 | -4
576491 | [RD_DEV][W3A] EtherCAT IO 映射表提供 sub channel 資訊給編譯器 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 4 | -4
576481 | [RD_DEV]新增台達裝置從裝置樹批次添加功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 12 | 12 | 0
576480 | [RD_DEV]新增總線裝置批次添加功能 | Designer Rev1.14.0 Sprint2 | Task | Completed | 12 | 12 | 0
574667 | [RD_DEV] EtherCAT_Tag_Table 變數名稱異常 | Designer Rev1.14.0 Plan | Task | Completed | 8 | 4 | -4
574070 | [RD_DEV]排除 B5 EtherCAT 下載遇到問題 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 2 | 2
569004 | [RD_DEV] DVPSEC - 設備主體: 上載管理員: EtherCAT節點Checksum與設備上載回的Checksum不一致 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0
564806 | [RD_DEV]當使用者配置的 EtherCAT 從站項目，有超出 FECAT 或 DVP-ES3(TEC) 限制的 pdo entry數量時，跳出警告 | Designer Rev1.14.0 Plan | Task | In Progress | 24 | 12 | -12
562191 | [RD_DEV] 若轉換成 AS300 系列，且有配置 EtherCAT 時，需自動配置 AS-FECAT 卡 | Designer Rev1.14.0 Plan | Task | Assigned | 4 | 0 | -4
562188 | [RD_DEV] DVP-ES3(TEC) 機種轉換成 AS300 時，保留 EtherCAT 配置、EtherCAT IO 映射變數 | Designer Rev1.14.0 Plan | Task | Assigned | 4 | 0 | -4
524598 | [RD_DEV][W3A] EtherCAT 匯出 ENI（2026Q1） | Designer Rev1.14.0 Plan | Task | Assigned | 8 | 0 | -8
521971 | [RD_DEV] DVPSEC - ECAT: 驗證功能 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 0 | 0

## XAVIERA
XAVIERA.FAN 范珮欣
| Estimate(h) | TimeSpend(h) | Utilization | Tasks
| 179.0h | 64.4h | 36.0% | 28
ID | Summary | Planned For | Type | State | Estimate(h) | TimeSpend(h) | Diff(h)
582613 | [RD_DEV] CANopen: Third Party EDS ( XN270325V1042 )匯入後, PDO Mapping 列表為空 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 1.5 | 1.5
581513 | [RD_DEV] 匯入 CANopen EDS 時, 從站識別資訊組成CANopen EDS 檔名需考量10進制與16進制轉換 | Designer Rev1.14.0 Sprint3 | Task | Completed | 0 | 4 | 4
579571 | [RD_DEV] W3A上載新增設備時, 須初始化 Embedded Device 通訊 | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 10.5 | -13.5
579524 | [RD_DEV] Corner 模擬器修改 Type 名稱 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 2.6 | 2.6
579204 | [RD_DEV] VFD: online 時, 狀態列顯示錯誤 | Designer Rev1.14.0 Sprint2 | Task | Completed | 3 | 2.5 | -0.5
578959 | [RD_DEV] AS332EC - 通訊: 設備無程式, 上載 Project CompactBin, 沒有上載結束事件 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 0.5 | 0.5
578955 | [RD_DEV] AS332EC - 通訊: 特定韌體版本, 下載AppCompactBin 失敗 | Designer Rev1.14.0 Sprint2 | Task | Completed | 0 | 1.5 | 1.5
576561 | [RD_DEV] CANopen 上載還原, 誤覆蓋 NW 中的 CANopen 主站 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 1 | 1
575221 | [RD_DEV] DVPSEC - 通訊: 上載 App Compact Bin, 固化方案版號, Program Checksum | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 1 | -3
575219 | [RD_DEV] DVPSEC - 通訊: 下載 Program Checksum 與 固化方案版號 | Designer Rev1.14.0 Sprint2 | Task | Completed | 4 | 0.5 | -3.5
575110 | [RD_DEV] CANopen 掃描通訊: 提供 Unknown Device 的識別資訊 | Designer Rev1.14.0 Sprint3 | Task | Completed | 8 | 3 | -5
574832 | [RD_DEV] MA500_通訊設定 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0.5 | -3.5
574831 | [RD_DEV] MA500_變頻精靈 | Designer Rev1.14.0 Sprint3 | Task | Completed | 4 | 0.5 | -3.5
574816 | [RD_DEV] APF3000_通訊設定 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 4 | 0 | -4
574815 | [RD_DEV] APF3000_變頻精靈 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 4 | 0 | -4
574659 | [RD_DEV] AS332EC - 通訊: 取得 Program Checksum 與 固化方案版號 | Designer Rev1.14.0 Sprint2 | Task | Completed | 8 | 1.6 | -6.4
574652 | [RD_DEV] AS332EC - 通訊: 下載 固化方案版號 與 Program Checksum | Designer Rev1.14.0 Sprint2 | Task | Completed | 12 | 6.1 | -5.9
574651 | [RD_DEV] AS332EC - 通訊: 上載 App Compact Bin | Designer Rev1.14.0 Sprint2 | Task | Completed | 24 | 5.1 | -18.9
574005 | [RD_DEV] 通訊設定: 驗證 W3A 預設站號為 200 | Designer Rev1.14.0 Sprint3 | Task | Completed | 1 | 0.5 | -0.5
574003 | [RD_DEV] 通訊設定: 預設站號從 DDF 取得 | Designer Rev1.14.0 Sprint3 | Task | Completed | 24 | 8 | -16
573065 | [RD_DEV] 架構圖更新 (Communication part) - DIADesigner v1.14.0 | Rev1.14.0 DIADesigner | Task | Assigned | 0 | 0 | 0
568350 | [RD_DEV] AS332EC - Survey: 上載後可直接Online 不須新編譯, 通訊需求討論 | Designer Rev1.14.0 Sprint1 | Task | Completed | 0 | 5 | 5
525572 | [RD_DEV] AS332EC - 設備主體: Compact bin 改善File Size | Designer Rev1.14.0 Sprint3 | Task | Assigned | 8 | 0 | -8
521989 | [RD_DEV] DVPSEC - Embedded Corner下載管理員: Post Download | Designer Rev1.14.0 Sprint3 | Task | Resolved | 8 | 6.5 | -1.5
521977 | [RD_DEV] DVPSEC - 設備能力透過外部檔案取得 | Designer Rev1.14.0 Sprint2 | Task | Assigned | 4 | 0 | -4
521973 | [RD_DEV] DVPSEC - 通訊 連線至模擬器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 3 | 0 | -3
507452 | [RD_DEV] AS332EC - 通訊: 連線至模擬器 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 4 | 2 | -2
505507 | [RD_DEV] AS332EC - 設備能力透過外部檔案取得 | Designer Rev1.14.0 Sprint3 | Task | Assigned | 24 | 0 | -24